REPUBLIC OF KENYA

MIGORI COUNTY

BUDGET IMPLEMENTATION REVIEW REPORT

FIRST QUARTER OF

FY 2024/2025

OCTOBER, 2024

Table of Contents

LIST OF TABLES.	ii

FOREWORD	iii

ACKNOWLEDGEMENT	iv

SECTION ONE: INTRODUCTION	5

1.1 OBJECTIVES OF CBIRR	5

1.2 SIGNIFICANCE OF CBIRR	5

1.3 STRUCTURE OF CBIRR	5

1.4 Legal Basis	5

1.1.1	Overview of FY 2024/25 Budget	7

1.1.2	Revenue Performance	7

Table 3.175: Migori County, Revenue Performance in the First Quarter of FY 2024/25	7

Figure 104: Trend in Own-Source Revenue Collection from the First Quarter of FY 2019/20 to the First Quarter of FY 2024/25	9

Figure 105: Top Streams of Own Source Revenue in the First Quarter FY 2024/25	9

1.1.3	Borrowing by the County	10

1.1.4	Exchequer Issues	10

1.1.5	County Expenditure Review	10

1.1.6	Settlement of Pending Bills	10

1.1.7	Expenditure by Economic Classification	10

Table 3.176: Summary of Budget and Expenditure by Economic Classification	10

1.1.8	Expenditure on Employees’ Compensation	12

Figure 106: Percentage of Wage Bill to Total Revenue from the First Quarter of FY 2018/19 to the First Quarter of FY 2024/25	12

1.1.9	County Emergency Fund and County-Established Funds	12

Table 3.177: Performance of County Established Funds in the First Quarter of FY 2024/25	12

1.1.10	Expenditure on Operations and Maintenance	13

Figure 107: Migori County, Operations and Maintenance Expenditure by Major Categories	14

1.1.11	Facility Improvement Financing	15

Table 3.178: Breakdown of expenditure by health facilities in the first quarter of FY 2024/25	15

1.1.12	Development Expenditure	15

Table 3.179: Migori County, List of Development Projects with the Highest Expenditure	16

1.1.13	Budget Performance by Department	17

Table 3.180: Migori County, Budget Allocation and Absorption Rate by Department	17

1.1.14	Budget Execution by Programmes and Sub-Programmes	18

Table 3.181: Migori County, Budget Execution by Programmes and Sub-Programmes	19

1.1.15	Accounts Operated in Commercial Banks	36

1.1.16	Key Observations and Recommendations	36

# LIST OF TABLES.

Table 1: Annual Budget allocation against the Actual Receipts	7

Table 2: Analysis of revenue receipts for FY 2023/24	10

Table 3: Comparison of budget against actual receipts of the revenue streams for the FYs 2023/24 and 2024/25	10

Table 4: Conditional/ Donor Funds Budgeted Against Actual Receipts for FY 2024/25	12

Table 5: The top 5 performing revenue streams for the FY 2023/24	14

Table 6: Exchequer release as a percentage of the total revenue received	15

Table 7: Total Exchequer Issues in   FY 2024/25	15

Table 8: Summary of Budgeted Versus Actual Expenditure by Economic Classification for FY 2024/25	16

Table 9: Expenditure analysis by economic classification	17

Table 10: Migori County Health Facilities Expenditure Performance in FY 2024/25	18

Table 11: Analysis of budget performance by department	19

Table 12: Fiscal Projections	31

Table 13: Fiscal Projections for FY 2026/27 by Sector	32

# FOREWORD

The County Budget Implementation Review Report (CBIRR) for the Financial Year 2024/25 is prepared pursuant to Section 118 of the Public Finance Management (PFM) Act, 2012 and the PFM (County Governments) Regulations, 2015. This statutory document provides a detailed review of the County’s fiscal performance for First quarter of FY 2024/25 against budgetary allocations, assesses recent macroeconomic developments, and outlines the fiscal outlook

The CBIRR is published at a time when the County Government of Migori continues to navigate a constrained fiscal environment characterized by revenue shortfalls, delayed disbursement of conditional grants, and rising expenditure pressures. Despite these challenges, the County has made significant strides in enhancing Own Source Revenue (OSR) collection, improving budget absorption, and implementing priority programs aligned with the County Integrated Development Plan (CIDP III) and the Fourth Medium Term Plan.

The fiscal performance for first quarter of FY 2024/25 reflects broad compliance with the fiscal responsibility principles outlined in the PFM Act, including maintaining recurrent expenditure within total revenue, allocating at least 30 percent of the budget to development programs, and keeping the wage bill within the prescribed threshold. The County Government remains committed to sustaining fiscal discipline, strengthening revenue administration, and prioritizing high-impact interventions that promote inclusive growth and service delivery.

Maurice Otunga

CECM – Finance & Economic Planning

# ACKNOWLEDGEMENT

The preparation of the County Budget Implementation Review Report (CBIRR) for the first quarter of the Financial Year 2024/25 marks a significant milestone in the County’s commitment to prudent financial management and evidence-based planning. This document has been developed in accordance with the provisions of the Public Finance Management (PFM) Act, 2012 and the PFM (County Governments) Regulations, 2015.

The successful completion of this CBIRR was made possible through the collaborative efforts of various stakeholders. We extend our sincere appreciation to all County Departments and Sector Working Groups (SWGs) for their timely submission of budget execution reports and provision of relevant data and insights. Their contributions were instrumental in compiling the fiscal performance review and shaping the medium-term outlook.

We acknowledge the technical team within the Department of Finance and Economic Planning for their dedication in consolidating, analyzing, and aligning the document with statutory requirements and policy priorities. Special thanks go to the County Assembly for its oversight role and to the Controller of Budget for providing exchequer release data that informed the expenditure analysis. We are also grateful to development partners and the public for their valuable input during the consultative forums held across all sub-counties. Their feedback enriched the document and ensured that the fiscal strategy reflects the aspirations and needs of Migori County residents.

I wish to thank all departments, entities, and stakeholders who contributed to the preparation of this document. Your continued support and collaboration remain critical in advancing the County’s fiscal and development objectives.

Dr. Achuora John Odoyo

Chief Officer – Finance and Economic Planning

# SECTION ONE: INTRODUCTION

This County Budget Implementation Review Report (CBIRR) for first quarter of FY 2024/25 is prepared in accordance with Section 118 of the Public Finance Management (PFM) Act, 2012 and the PFM (County Governments) Regulations, 2015. It presents a review of the actual fiscal performance for first quarter of FY 2024/25 against budgetary allocations, assesses recent economic developments, and outlines implications for the fiscal outlook as set out in the County Fiscal Strategy Paper (CFSP) 2025.

## 1.1 OBJECTIVES OF CBIRR

The 2025 CBIRR provides a review of the first quart of FY 2024/2025 fiscal and non-fiscal performance and their impact on the financial objectives and fiscal responsibilities set out in the CFSP prepared in line with the budget policy statement. The first quarter CBIRR provides indicative ceilings which will guide the budget preparation process.

## 1.2 SIGNIFICANCE OF CBIRR

The CBIRR is a key policy document that links planning with budgeting. It plays a critical role in the budget-making process within the MTEF framework by reviewing fiscal performance for the first quarter of FY 2024/25 and identifying deviations from the budget. This enables the County Government to make realistic forecasts for the upcoming fiscal year.

## 1.3 STRUCTURE OF CBIRR

The paper is organized into five sections:

- Section I: Introduction and objectives of CBIRR;

- Section II: Review of fiscal performance in first quarter of FY 2024/25, subdivided into: overview of the budget, revenue analysis, and overall expenditure review;

- Section III: Recent economic developments and updated macroeconomic outlook, including: macroeconomic trends, domestic growth outlook, and risks;

- Section IV: Resource allocation framework, including revenue and expenditure projections for FY 2025/26 and the medium term;

- Section V: Conclusion, highlighting the purpose and next steps.

## 1.4 Legal Basis

The County Budget Implementation Review Report is prepared in accordance with Section 118 of the Public Financial Management Act, 2012. The law states that:

- The County Treasury shall prepare and submit to County Executive committee for approval, by 30th September in each financial year, a County Budget Implementation Review Report which shall include:

- Actual fiscal performance in the previous financial year compared to the budget appropriation for that year;

- Updated economic and financial forecasts with sufficient information to show changes from the forecasts in the most recent County Fiscal strategy paper

- Information on how actual financial performance for the previous financial year may have affected compliance with the fiscal responsibility principles or the financial objectives in the latest County Fiscal strategy paper; and

- The    reasons    for    any    deviation    from    the    financial    objectives    together with proposals to address the deviation and the time estimated to do so.

- County Executive committee shall consider the County Budget Implementation Review Report with a view to approving it with or without amendments, not later than fourteen days after its submission.

- Not later than seven days after the CBIRR has been approved by Executive committee, the County Treasury shall:

- Submit the paper to the Budget and appropriation    Committee of the County Assembly to be laid before the County assembly; and

- Publish and publicise the paper not later than fifteen days after laying the Paper before County Assembly.

Fiscal Responsibility Principles in the Public Financial Management Law

In line with the Constitution, the new Public Financial Management (PFM) Act, 2012, sets   out   the   fiscal   responsibility   principles   to   ensure   prudency   and transparency in the management of public resources.  The PFM law (Section 107(b)) states that:

- The county government’s recurrent expenditure shall not exceed the county government’s total revenue

- Over the medium term, a minimum of 30% of the County budget shall be allocated to development expenditure

- The County government’s expenditure on wages and benefits for public officers shall not exceed a percentage of the County government revenue as prescribed by the regulations.

- Over the medium term, the County government’s borrowings shall be used only for the purpose of financing development expenditure and not for recurrent expenditure.

- Public debt and obligations shall be maintained at a sustainable level as approved by County Government (CG)

- Fiscal risks shall be managed prudently

A reasonable degree of predictability with respect to the level of tax rates and tax bases shall be maintained, taking into account any tax reforms that may be made in the future on.

### Overview of FY 2024/25 Budget

The Migori County approved FY 2024/25 budget is Kshs.10.39 billion. It comprised Kshs.3.44 billion (33 per cent) and Kshs.6.95 billion (67 per cent) allocation for development and recurrent programmes, respectively. The budget estimates represent an increase of Kshs.350.43 million (4 per cent) from the FY 2023/24 budget, which comprised a development budget of Kshs.3.07 billion and a recurrent budget of Kshs6.96 billion. The increase in the county government budget was attributed to the anticipated additional allocation of revenues from new emerging grants in the County revenue portfolio envelope.

The Migori County Government budget will be financed from different sources of revenue. These include Kshs.8.34 billion (80 per cent) expected from the National Government as the equitable share of revenue raised nationally, Kshs.1.43 billion (14 per cent) as additional allocations, Kshs.620 million (6 per cent) generated as gross own source revenue. The own-source revenue includes Kshs.140 million (22.6 per cent) as Facility Im-provement Fund (revenue from health facilities) and Kshs.480 million (77 per cent) as ordinary own-source revenue. A breakdown of the additional allocations is provided in Table 3.176.

### Revenue Performance

In the first quarter of FY 2024/25, the County received Kshs.1.56 billion to fund recurrent and development activities. The equitable share from the national government was Kshs.709.02 million, and additional alloca-tions from government and development partners were Kshs.65.13 million, and its own-source revenue (OSR) collection was Kshs.101.82 million. In addition, the County had a cash balance of Kshs.688.43 million from FY 2023/24, which was not included in the budget. Included in the balance brought forward is Kshs.667.32 million June 2024 equitable share that was disbursed in July 2024.

Analysis of the total OSR collection of Kshs.101.82 billion indicates that it included Facilities Improvement Fi-nancing (FIF) of Kshs.35.66 million and Kshs.66.16 million as ordinary OSR. Table 3.175 summarises the total revenue available to the county government during the first quarter of FY 2024/25.

#### Table 3.175: Migori County, Revenue Performance in the First Quarter of FY 2024/25

| S/No. | Revenue Category | Annual Budget Allo-cation (Kshs) | Actual Receipts (Kshs.) | Actual Receipts as Percentage of Annu-al Budget Allocation (%) |
| --- | --- | --- | --- | --- |
| A | Equitable Share of Revenue Raised Nationally | 8,341,446,108 | 709,022,919 | 9 |
| Subtotal |  | 8,341,446,108 | 709,022,919 | 9 |
| B | Additional Allocations |  |  |  |
| 1. | DANIDA Grant (Universal Healthcare in De-volved System Program) | 12,358,500 | - | 0 |
| 2. | IDA (World Bank) Credit for National Agricultural and Rural Inclusive Growth Project (NARIGP) | 5,000,000 | - | 0 |
| 3. | EU Grant for Instrument for Devolution Advice and Support (IDEAS) | 5,706,628 | - | 0 |

| S/No. | Revenue Category | Annual Budget Allo-cation (Kshs) | Actual Receipts (Kshs.) | Actual Receipts as Percentage of Annu-al Budget Allocation (%) |
| --- | --- | --- | --- | --- |
| 4. | Sweden - Agricultural Sector Development Sup-port Programme (ASDSP) II | 1,120,452 | - | 0 |
| 5. | Climate Change | 11,000,000 | 11,000,000 | 100 |
| 6. | A grant from National Government - Industrial Park | 250,000,000 | 54,131,579 | 22 |
| 7. | National Agricultural Value Chain Development Project (NAVCDP) | 250,000,000 | - | 0 |
| 8. | KABDP SIDA | 10,918,919 | - | 0 |
| 9. | KABDP MOA&LD (GOK) | 1,000,000 | - | 0 |
| 10. | Aquaculture Business Development Project (ABDP) | 13,617,785 | - | 0 |
| 11. | Livestock Value Chain Support Project | 14,323,680 | - | 0 |
| 12. | Climate Change - German Development Bank (KFW) - (FLLoCA -CCRI Grant) | 200,000,000 | - | 0 |
| 13. | Kenya Devolution Support Program II | 37,500,000 | - | 0 |
| 14. | Kenya Water and Sanitation (K-WASH) Pro-gram | 199,874,000 | - | 0 |
| 15. | Urban Institutional Grant (UIG) | 35,000,000 | - | 0 |
| 16. | Migori Municipality URB Development Grant | 54,181,008 | - | 0 |
| 17. | Awendo Municipality URB Development Grant | 16,800,000 | - | 0 |
| 18. | Rongo Municipality URB Development Grant | 16,800,000 | - | 0 |
| 19. | Kehancha Municipality URB Development Grant | 16,800,000 | - | 0 |
| 20. | Leasing of Medical Equipment | 124,723,404 | - | 0 |
| 21. | Fertiliser Subsidy | 144,621,807 | - | 0 |
| 22. | Allocation for Court fines | 974,165 | - | 0 |
| 23. | Allocation for Mineral Royalties | 3,125,408 | - | 0 |
| Subtotal |  | 1,425,445,756 | 65,131,579 | 5 |
| C | Own Source Revenue |  |  |  |
| 24. | Ordinary Own Source Revenue | 480,000,000 | 66,158,735 | 14 |
| 26. | Facility Improvement Fund (FIF) | 140,000,000 | 35,658,735 | 26 |
| Subtotal |  | 620,000,000 | 101,817,470 | 16 |
| D | Other Sources of Revenue |  |  |  |
| 27. | Unspent balance from FY 2022/23 | - | 688,425,652 | 0 |
| Sub Total |  | - | 688,425,652 | 0 |
| Grand Total |  | 10,386,891,864 | 1,564,397,620 | 15 |

Source: Migori County Treasury

Figure 104 shows the trend in own-source revenue collection from the First Quarter of FY 2019/20 to the First Quarter of FY 2024/25.

#### Figure 104: Trend in Own-Source Revenue Collection from the First Quarter of FY 2019/20 to the First Quarter of FY 2024/25

Source: Migori County Treasury

During the first quarter of FY 2024/25, the County generated Kshs.101.82 million from its revenue sources, including FIF. This amount was an increase of 12 per cent compared to Kshs.91.28 million realised in a similar period in FY 2023/24. This was 16 per cent of the annual target and 14 per cent of the equitable revenue share disbursed. The increase is attributed mainly to the automation of some revenue streams, such as single business permits and tax law enforcement.

The revenue streams which contributed the highest OSR receipts are shown in Figure 105.

#### Figure 105: Top Streams of Own Source Revenue in the First Quarter FY 2024/25

Source: Migori County Treasury

The highest revenue stream, Kshs.35.66 million, was from Health/Hospital Fees/FIF, contributing 35 per cent of the total OSR receipts during the reporting period.

### Borrowing by the County

The County Assembly of Migori secured an overdraft of Kshs.50 million from the Kenya Commercial Bank Ltd, Migori Branch, as a short-term credit facility at an interest rate of 3 per cent, payable within the credit facility period of one month. The short-term borrowing was sought to pay Members of the County Assembly and Staff allowances arrears for the financial year 2023/24 and finance office operations during the month of July 2024 as a result of delays in disbursement of June 2024 National shareable revenue by the National Treasury. The amount was still outstanding as of 30 September 2024.

### Exchequer Issues

During the reporting period, the Controller of Budget approved withdrawals of Kshs.1.01 billion from the CRF account comprised Kshs.195.20 million (19.3 per cent) for development programmes and Kshs.816.82 million (81 per cent) for recurrent programmes. Analysis of the recurrent exchequers released in the FY 2023/24 in-dicates that Kshs.583.84 million was released towards Employee Compensation and Kshs.232.99 million for Operations and Maintenance expenditure.

As of 30 September 2024, the county government’s cash balance in the CRF account was Kshs.520.64 million.

### County Expenditure Review

In the reporting period, the County spent Kshs.891.35 million on development and recurrent programmes. The expenditure represented 88 per cent of the total funds released by the CoB and comprised Kshs.172.07 million and Kshs.719.29 million on development and recurrent programmes, respectively. Expenditure on develop-ment programmes represented an absorption rate of 5 per cent, while recurrent expenditures represented 10 per cent of the annual recurrent expenditure budget.

### Settlement of Pending Bills

The County reported pending bills amounting to Kshs.1.94 billion as of 30 June 2024, comprising pending pay-ments by the County Executive of Kshs.1.76 billion and Kshs.184.72 million for the County Assembly.

The County Executive’s pending bills consist of Kshs.875.34 million for recurrent expenditures and Kshs.881.38 million for development expenditures. The County Executive settled pending bills amounting to Kshs.184.96 million in the reporting period, which consisted of Kshs.12.89 million for recurrent expenditure and Kshs.172.01 million for development programs. The County Assembly did not pay any pending bills during the reporting period. Therefore, the outstanding bills were Kshs.1.76 million as of 30 September 2024.

### Expenditure by Economic Classification

During the first quarter of FY 2024/25, the County Executive spent Kshs.507.13 million on employee com-pensation, Kshs.123.23 million on operations and maintenance, and Kshs.172.07 million on development ac-tivities. Similarly, the County Assembly spent Kshs.76.71 million on employee compensation and Kshs.12.22 million on operations and maintenance, as shown in Table 3.176.

#### Table 3.176: Summary of Budget and Expenditure by Economic Classification

| Expenditure Classification | Budget (Kshs.) |  | Expenditure (Kshs.) |  | Absorption (%) |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | County Executive | County Assembly | County Executive | County Assembly | County Executive | County Assembly |
| Total Recurrent Expenditure | 5,957,832,399 | 987,472,209 | 630,356,701 | 88,931,982 | 10 | 9 |
| Compensation to Employees | 3,131,999,955 | 491,676,066 | 507,126,714 | 76,708,851 | 16 | 16 |
| Operations and Maintenance | 2,825,832,444 | 495,796,143 | 123,229,987 | 12,223,131 | 4 | 3 |
| Development Expenditure | 3,391,587,256 | 50,000,000 | 172,066,772 | - | 5 | 0 |
| Total | 9,349,419,655 | 1,037,472,209 | 802,423,473 | 88,931,982 | 9 | 9 |

Source: Migori County Treasury

### Expenditure on Employees’ Compensation

In the first quarter of FY 2024/25, expenditure on employee compensation was Kshs.583.84 million, or 37 per cent of the available revenue, which amounted to Kshs.1.56 billion. This expenditure represented an increase of 0.5 per cent from Kshs.580.84 million reported in a similar period in FY 2023/24. The wage bill included Kshs.241.69 million paid to health sector employees, translating to 41.4 per cent of the total wage bill

Figure 106 shows the trend of personnel expenditures as a percentage of total revenue from the first quarter of FY 2018/19 to the first quarter of FY 2024/25.

#### Figure 106: Percentage of Wage Bill to Total Revenue from the First Quarter of FY 2018/19 to the First Quarter of FY 2024/25

Source: Migori County Treasury

The County Assembly spent Kshs.8.74 million on committee sitting allowances for the 60 MCAs against the annual budget allocation of Kshs.49.30 million. The average monthly sitting allowance was Kshs.48,557 per MCA. The County Assembly has established 27 Committees.

### County Emergency Fund and County-Established Funds

Section 116 of the PFM Act 2012 allows County Governments to establish other public funds with approval from the County Executive Committee and the County Assembly. The County allocated Kshs.160 million to county-established funds in FY 2024/25, constituting 1.5 per cent of the County’s overall budget. Further, the County did not allocate to the Emergency Fund contrary to Section 110 of the PFM Act, 2012.

Table 3.177 summarises each established Fund’s budget allocation and performance during the reporting period.

#### Table 3.177: Performance of County Established Funds in the First Quarter of FY 2024/25

| S/No. | Name of the Fund | Approved Budget Allocation in FY 2024/25 (Kshs.) | Exchequer Issues in the First Quarter of FY 2024/25 (Kshs.) | Actual Expen-diture in First Quarter of FY 2024/25 (Kshs.) | Cumulative disbursements to the Fund (Kshs)) | Submission of Annual Finan-cial Statements (Yes/No.) |
| --- | --- | --- | --- | --- | --- | --- |
|  | County Executive Established Funds |  |  |  |  |  |
| 1. | Migori County Executive Car Loans & House Mortgage Fund Scheme | - | - | - | 247,500,000 | Yes |
| 2. | Migori County Education Bursary Fund | 120,000,000 | - | - | 840,000,000 | Yes |

| S/No. | Name of the Fund | Approved Budget Allocation in FY 2024/25 (Kshs.) | Exchequer Issues in the First Quarter of FY 2024/25 (Kshs.) | Actual Expen-diture in First Quarter of FY 2024/25 (Kshs.) | Cumulative disbursements to the Fund (Kshs)) | Submission of Annual Finan-cial Statements (Yes/No.) |
| --- | --- | --- | --- | --- | --- | --- |
| 3. | Migori County Scholarships & Educational Benefits Fund | 20,000,000 | - | - | 279,000,000 | Yes |
| 4. | Migori County Alcoholic Drink Fund | - | - | - | 2,250,318 | Yes |
| 5. | Emergency Fund | - | - | - | - | Unregulated |
| 6. | Migori County SMEs Trade Development - Inua Biashara | - | - | - | 54,000,000 | Yes |
|  | County Assembly Established Funds |  |  |  |  |  |
| 7. | Migori County Assembly Car Loans & House Mortgage Fund Scheme | 20,000,000 | - | - | 236,000,000 | Yes |
|  | Total | 160,000,000 | - | - | 1,658,750,318 |  |

Source: Migori County Treasury

During the reporting period, the CoB received all the quarterly financial returns from the Fund Administrators, as indicated in

Table 3.54: Performance of County Established Funds in the First Quarter of FY 2024/25 3, contrary to the requirement of Section 168 of the PFM Act, 2012.

The County government uses commercial bank accounts to operate the above-established public funds con-trary to Regulations 82(1)(b) of the PFM (County Governments) Regulations, 2015, which require that County government bank accounts must be opened and maintained at the Central Bank of Kenya.

### Expenditure on Operations and Maintenance

Figure 107 summarises the Operations and Maintenance expenditure by major categories.

#### Figure 107: Migori County, Operations and Maintenance Expenditure by Major Categories

Source: Migori County Treasury

The expenditure on domestic travel amounted to Kshs.19.74 million, comprising Kshs.12.22 million spent by the County Assembly and Kshs.7.51 million by the County Executive. There was no expenditure on foreign travel. The operations and maintenance costs include an expenditure of Kshs.166,401 on garbage collection.

### Facility Improvement Financing

During the period under review, the County reported a collection of 35.66 million Kshs as FIF, which was 25.5 per cent of the annual target of Kshs.140 million. The collected amount was retained and utilised at source in line with the Facility Improvement Financing Act, 2023, where 72 per cent of the collection is disbursed to the County health facilities, 20 per cent was utilised in public health & sanitation, 5 per cent was retained at Hospi-tal Emergency Fund, and 3 per cent is spent as Health Management Board Administrative Expenses.

The expenditure by the health facilities amounted to Kshs.15.72 million, representing 11 per cent absorption. The expenditure does not include Kshs.9.96 million FIF revenues collected in September 2024, which were outstanding disbursements as of 30 September 2024 to the 16 health facilities listed in Table 3.178.

#### Table 3.178: Breakdown of expenditure by health facilities in the first quarter of FY 2024/25

| No. | Name of the Health Facility | Approved Budget for the Facility | Actual Expenditure of the Facility | Absorption rate (%) |
| --- | --- | --- | --- | --- |
| 1. | Migori County Referral Hospital | - | 7,336,809 | - |
| 2. | Kehancha Sub-County Hospital | - | 1,561,000 | - |
| 3. | Awendo Sub-County Hospital | - | 1,416,130 | - |
| 4. | Muhuru Sub-County Hospital | - | 1,037,000 | - |
| 5. | Isebania Sub-County Hospital | - | 825,400 | - |
| 6. | Uriri Sub County Hospital | - | 782,250 | - |
| 7. | Rongo Sub-County Hospital | - | 751,900 | - |
| 8. | Kegonga Sub-County Hospital | - | 620,651 | - |
| 9. | Macalder Sub-County Hospital | - | 499,000 | - |
| 10. | Nyamaraga Sub-County Hospital | - | 307,200 | - |
| 11. | Ntimaru Sub-County Hospital | - | 205,000 | - |
| 12. | Karungu Sub-County Hospital | - | 172,500 | - |
| 13. | Oyani Sub County Hospital | - | 58,140 | - |
| 14. | God Kwer Sub-County Hospital | - | 54,000 | - |
| 15. | Ongo Sub-County Hospital | - | 52,250 | - |
| 16. | Othoro Sub-County Hospital | - | 39,400 | - |
|  | Total | 140,000,000 | 15,718,630 | 11.2 |

Source: Migori County Treasury

The health FIF budget was consolidated as a one-line-item budget in FY 2024/25 approved budget under the Department of Health Medical Services. The Health Facility with the highest expenditure was Migori County Referral Hospital, followed by Kehancha Sub-County Hospital, Awendo Sub-County Hospital, and the Othoro Sub-County Hospital.

### Development Expenditure

In the First Quarter of FY 2024/25, the County reported spending Kshs.172.06 million on development pro-grammes, an increase of 25 per cent compared to a similar period in FY 2023/24, when the County spent Kshs.137.34 million. Table 3.179 summarises the development projects with the highest expenditure in the reporting period.

#### Table 3.179: Migori County, List of Development Projects with the Highest Expenditure

| No. | Sector | Project Name | Project Location | Contract Sum (Kshs) | Amount Paid to Date (Kshs) | Implementation Status (%) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Roads, Transport, Public Works & Infrastructural Development | Construction & Completion of Osiri Footbridge | Macalder Kanyarwanda | 24,494,034 | 24,494,034 | 100 % Complete |
| 2 | Health Medical Services | Supply & Delivery of Hospital Equipment at MCRH | Headquarters | 13,989,800 | 13,989,800 | 100 % Complete |
| 3 | Roads, Transport, Public Works & Infrastructural Development | Construction & Completion of Ombasa Footbridge | West Sakwa | 13,110,795 | 13,110,795 | 100 % Complete |
| 4 | Health Medical Services | Renovation Works on The Kehancha Sub-County Hospital | Bukira East | 9,998,982 | 9,998,982 | 100 % Complete |
| 5 | Health Medical Services | Construction of New OPD Block at Macalder Sub-County Hospital | Macalder Kanyarwanda | 9,993,999 | 9,993,999 | 100 % Complete |
| 6 | Agriculture, Live-stock, Veterinary Services, Fisheries & Blue Economy | Proposed Construction of Cold Rooms | Suna Central | 9,981,023 | 9,981,023 | 100 % Complete |
| 7 | Medical Services | Construction & Completion of Modern Health Products Ware-house Phase.1 | Suna Central | 9,978,622 | 9,978,622 | 100 % Complete |
| 8 | Trade, Tourism, Industry, Market & Co-operative Devel-opment | Construction & Completion of Ndiwa Market | North Kadem | 4,799,848 | 4,799,848 | 100 % Complete |
| 9 | Health Medical Services | Completion and Fixing of Works on Inter- nal Access Roads at Awendo Sub-County Hospital | Central Sakwa | 4,795,621 | 4,795,621 | 100 % Complete |
| 10 | Trade, Tourism, Industry, Market & Co-operative Devel-opment | Construction & Com-pletion of Bande Market Shade | Got Kachola | 4,599,354 | 4,599,354 | 100 % Complete |

Source: Migori County Treasury

### Budget Performance by Department

Table 3.180 summarises the departments’ approved budget allocation, expenditure, and absorption rate in the

first three months of FY 2024/25.

#### Table 3.180: Migori County, Budget Allocation and Absorption Rate by Department

| Department | Budget Allocation (Kshs. Million) |  | Exchequer Issues (Kshs. Million) |  | Expenditure (Kshs. Million) |  | Expenditure to Exchequer Issues (%) |  | Absorption rate (%) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Rec | Dev | Rec | Dev | Rec | Dev | Rec | Dev | Rec | Dev |
| Agriculture, Livestock, Veterinary Services, Fish-eries & Blue Economy | 244.69 | 532.31 | 30.27 | 22.35 | 26.30 | 22.35 | 86.9 | 100 | 10.7 | 4.2 |
| Trade, Tourism, Industry, Market & Co-operative Development | 156.11 | 330 | 11.27 | 15.96 | 11.06 | 15.96 | 98.1 | 100 | 7.1 | 4.8 |
| Health Medical Services | 1,592.57 | 354.72 | 287.62 | 61.41 | 277.73 | 52.76 | 96.6 | 85.91 | 17.4 | 14.9 |

| Department | Budget Allocation (Kshs. Million) |  | Exchequer Issues (Kshs. Million) |  | Expenditure (Kshs. Million) |  | Expenditure to Exchequer Issues (%) |  | Absorption rate (%) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Rec | Dev | Rec | Dev | Rec | Dev | Rec | Dev | Rec | Dev |
| Education, Gender in-clusivity, Social Services, Youth and Sports | 518.84 | 100 | 61.42 | - | 56.10 | - | 91.3 | - | 10.8 | - |
| Roads, Transport, Public Works & Infrastructural Development | 150.38 | 770 | 13.15 | 46.30 | 10.15 | 46.30 | 77.2 | 100 | 6.7 | 6.0 |
| Lands, Physical Planning, Housing & Urban Devel-opment | 108.93 | 95 | 10.74 | 14.49 | 8.74 | - | 81.4 | - | 8.0 | - |
| Rongo Municipality | 20 | 26.80 | 0.49 | - | - | - | - | - | - | - |
| Kehancha Municipality | 21 | 26.80 | 1.90 | 4.39 | - | 4.39 | - | 100 | - | 16.4 |
| Migori Municipality | 20 | 64.18 | - | - | - | - | - | - | - | - |
| Awendo Municipality | 20 | 26.80 | - | - | - | - | - | - | - | - |
| Environment, Natural Re-sources, Climate Change & Disaster Management | 203.52 | 265.10 | 14.88 | - | 13.83 | - | 92.9 | - | 6.8 | - |
| Finance and Economic Planning | 965.01 | 20 | 137.17 | 4.65 | 117.95 | 4.65 | 86.0 | 100 | 12.2 | 23.2 |
| Public Service Man-agement, Monitoring & Evaluation & Performance Contracting | 738.78 | 40 | 54.35 | - | 58.75 | - | 108.1 | - | 8.0 | - |
| County Executive | 551.62 | 140 | 56.69 | 1.50 | 32.38 | 1.50 | 57.1 | 100 | 5.9 | 1.1 |
| County Assembly | 987.47 | 50 | 88.93 | - | 88.93 | - | 100.0 | - | 9.0 | - |
| Water and Energy | 149.55 | 399.87 | 14.80 | 19.60 | 13.05 | 19.60 | 88.2 | 100 | 8.7 | 4.9 |
| Public Health & Sanitation | 368.83 | 200 | 33.14 | 4.56 | 4.32 | 4.56 | 13.0 | 100 | - | 2.3 |
| Office of the County Attorney | 128 | - | - | - | - | - | - | - | - | - |
| Total | 6,945.30 | 3,441.59 | 816.82 | 195.20 | 719.29 | 172.07 | 88.1 | 88.15 | 10.4 | 5.0 |

Source: Migori County Treasury

Analysis of department expenditure shows that the Department of Finance and Economic Planning recorded the highest absorption rate of the development budget at 23.2 per cent, followed by the Kehancha Municipality at 16.4 per cent. The Department of Health Medical Service had the highest percentage of recurrent expendi-ture to budget at 17.4 per cent. In contrast, two departments & four municipalities, namely Public Health & Sanitation, Office of the County Attorney, Rongo Municipality, Kehancha Municipality, Migori Municipality and Awendo Municipality respectively did not have any recurrent expenditure.

### Budget Execution by Programmes and Sub-Programmes

Table 3.181 summarises the budget execution by programmes and sub-programmes in the First Quarter of FY 2024/25.

#### Table 3.181: Migori County, Budget Execution by Programmes and Sub-Programmes

| Programme | Sub-Programme | Approved Estimates FY 2024/25 |  | Actual Expenditure as of 30 September 2024 |  | Absorption Rate (%) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Recurrent | Development | Recurrent | Develop-ment | Rec | Dev |
| Department of County Executive |  |  |  |  |  |  |  |
| General ad-ministration & support services | General Administration (Office of The Governor) | 174,065,257 | 140,000,000 | 28,024,784 | 1,499,961 | 16.1 | 1.1 |
|  | Administrative services (County Secretary) | 33,900,000 |  | 2,050,000 |  | 6.0 | - |
|  | Administrative services (Deputy Governor) | 31,000,000 |  | 2,050,000 |  | 6.6 | - |
|  | General administra-tion services (ICT) | 40,000,000 |  | 252,291 |  | 0.6 | - |
|  | Administrative & support services (Special Programs) | 20,050,000 | - | - | - | - | - |
| Governance & Administration Services | Governor’s Statehouse Services | 22,000,000 | - | - | - | - | - |
|  | Co-ordination and Supervision Services | 16,000,000 | - | - | - | - | - |
|  | Lake Region Economic Bloc | 5,000,000 | - | - | - | - | - |
|  | Council of Governors | 5,000,000 | - | - | - | - | - |
|  | Liaison office - Nairobi | 5,000,000 | - | - | - | - | - |
|  | Chief of Staff | 5,000,000 | - | - | - | - | - |
|  | Protocol Office | 5,000,000 | - | - | - | - | - |
|  | Security Services | 7,000,000 | - | - | - | - | - |
|  | Communication and Press | 6,000,000 | - | - | - | - | - |
|  | Political Advisor | 5,000,000 | - | - | - | - | - |
|  | Economic Advisor | 5,000,000 | - | - | - | - | - |
|  | Security Services | 1,000,000 | - | - | - | - | - |
| County secretary services | County secretary service. | 21,600,000 | - | - | - | - | - |
| Cohesion & Peacebuilding | Peace Building Initiatives | 8,000,000 | - | - | - | - | - |
|  | Conflict management & resolution | 10,000,000 | - | - | - | - | - |
| Research & Education | Research & Education Services | 2,000,000 | - | - | - | - | - |
| Geospatial infor-mation services. | Geospatial informa-tion services | 5,000,000 | - | - | - | - | - |
| Performance management services | Performance Management services. | 4,000,000 | - | - | - | - | - |
| ICT Infrastructure | ICT infrastructure & connectivity | 12,000,000 | - | - | - | - | - |
| Communication services | Communication services | 10,000,000 | - | - | - | - | - |
| E-governance | Automation services | 5,254,743 | - | - | - | - | - |
| E-learning | Digital curriculum integration & development. | 1,200,000 | - | - | - | - | - |

| Programme | Sub-Programme | Approved Estimates FY 2024/25 |  | Actual Expenditure as of 30 September 2024 |  | Absorption Rate (%) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Recurrent | Development | Recurrent | Develop-ment | Rec | Dev |
| Digital innova-tion | Innovation services | 1,600,000 |  |  |  | - | - |
| Resource Mobili-sation Services | Resource Mobilisation services | 12,550,000 |  |  |  | - | - |
| Cohesion & Peacebuilding | Civic Education | 4,900,000 |  |  |  | - | - |
|  | Peace Building Initiatives | 12,400,000 |  |  |  | - | - |
| External partnerships & affairs | External partners’ relations management | 55,100,000 |  |  |  | - | - |
| Sub-Total |  | 551,620,000 | 140,000,000 | 32,377,075 | 1,499,961 | 5.9 | 1.1 |
| Office of the County Attorney |  |  |  |  |  |  |  |
| General ad-ministration & support services | Finance & Administration | 29,278,400 | - | - | - | - | - |
| Legal Services | Advisory & Research services | 2,900,000 | - | - | - | - | - |
|  | Staff Development | 1,700,000 | - | - | - | - | - |
|  | Legal compliance services | 94,121,600 | - | - | - | - | - |
| Sub-Total |  | 128,000,000 | - | - | - | - | - |
| Department of Public Service Management, Monitoring and Evaluation and Performance Contracting |  |  |  |  |  |  |  |
| General Ad-ministration & Support Services | Administrative Sup-port Services (PSM) | 574,727,694 |  | 52,872,841 |  | 9.2 | - |
|  | General Administra-tion Services (PSB) | 57,600,000 |  | 5,743,186 |  | 10.0 | - |
|  | Administrative Sup-port Services (M&E) | 5,400,000 |  |  |  | - | - |
|  | Efficient Monitoring & Evaluation | 7,600,000 |  |  |  | - | - |
| Human Capital Management & Development Services | Human Resource Management Services | 6,355,162 |  |  |  | - | - |
| Devolved Units Administration Services | Devolved Units Ad-ministration Services | 17,300,000 |  | 132,500 |  | 0.8 | - |
|  | Devolved Units (Ward) Development Programme | - | 40,000,000 | - | - | - | - |
| Civic Education & Public Partici-pation | Civic Education services | 3,000,000 | - | - | - | - | - |
| Public Commu-nication & Re-cords Manage-ment Services | Record management programme | 1,600,000 | - | - | - | - | - |
| Record manage-ment pro-gramme | Public Communica-tions | 1,300,000 | - | - | - | - | - |
| Kenya Devo-lution Support Program II | Kenya Devolution Support Program II | 37,500,000 | - | - | - | - | - |

| Programme | Sub-Programme | Approved Estimates FY 2024/25 |  | Actual Expenditure as of 30 September 2024 |  | Absorption Rate (%) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Recurrent | Development | Recurrent | Develop-ment | Rec | Dev |
| County Security and Compliance Enforcement Services | Support and administration services | 6,500,000 | - | - | - | - | - |
| Public Service Board services | Public Service Board services | 10,500,000 | - | - | - | - | - |
| National values & principles of governance | National Values & Principles of Governance | 8,900,000 | - | - | - | - | - |
| Information & records manage-ment | Records management services | 500,000 | - | - | - | - | - |
| Sub-Total |  | 738,782,856 | 40,000,000 | 58,748,527 | - | 8.0 | - |
| Department of Agriculture, Livestock, Veterinary Services, Fisheries & Blue Economy |  |  |  |  |  |  |  |
| General Ad-ministration & Support Services | Administrative services | 166,205,394 | - | 26,303,743 | - | 15.8 | - |
|  | Administrative services (Livestock) | 8,383,562 | - | - | - | - | - |
|  | Administrative services (Vet) | 7,393,362 | - | - | - | - | - |
|  | Administrative services (Fisheries) | 19,131,200 | - | - | - | - | - |
| Agricultural Pol-icy & Planning | Policies & Legal Framework | 4,963,000 | - | - | - | - | - |
| Policies & Legal Framework | Policy & planning services (Fisheries) | 1,000,000 | - | - | - | - | - |
| Agricultural Ex-tension services | Field extension services & support | 18,441,649 | - | - | - | - | - |
| Crop Development & Management | Crop Development | - | 18,041,500 |  | 15,775,260 | - | 87.4 |
| Agribusiness Development | Agribusiness Development | 4,641,984 |  |  |  | - | - |
| Pending Bills | Pending Bills (Agriculture) | - | 6,958,500 |  |  | - | - |
| Donor Funds | Donor Funds (Agriculture | - | 428,367,806 |  |  | - | - |
|  | Donor Funds (Livestock) | - | 14,323,680 |  |  | - | - |
|  | Donor Funds (Fisheries) | - | 13,617,785 |  |  | - | - |
| Livestock extension & support services | Extension services | 6,640,000 |  |  |  | - | - |
| Livestock market development | Market support infrastructure | - | 2,000,000 |  | 1,697,328 | - | 84.9 |
| Livestock enterprise development & value addition | Livestock enterprise development | - | 1,000,000 |  |  | - | - |
| Livestock breeds improvement | Livestock multiplica-tion & upgrading | - | 15,400,000 |  | 4,873,822 | - | 31.6 |

| Programme | Sub-Programme | Approved Estimates FY 2024/25 |  | Actual Expenditure as of 30 September 2024 |  | Absorption Rate (%) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Recurrent | Development | Recurrent | Develop-ment | Rec | Dev |
| Livestock climate change adaptation & mitigation | Livestock-focused climate risk management | - | 1,600,000 | - | - | - | - |
| Livestock disease & pest control management | Disease & pest control | 1,300,000 | 4,000,000 | - | - | - | - |
|  | Disease surveillance |  | 3,000,000 | - | - | - | - |
| Livestock breeding & live-stock products improvement | Breeds selection & artificial insemination | 1,200,000 |  | - | - | - | - |
| Veterinary pub-lic health | Meat hygiene services | 375,000 | 1,000,000 | - | - | - | - |
| Veterinary extension & clin-ical services | Extension services | 600,000 |  | - | - | - | - |
| Aquaculture development | Aquaculture produc-tion systems | - | 5,600,000 | - | - | - | - |
|  | Fish breeding & stock-ings services | - | 2,000,000 | - | - | - | - |
|  | Fish feeds & feeding services | - | 2,400,000 | - | - | - | - |
| Fish marketing & value addition | Fish marketing ser-vices | - | 4,300,000 | - | - | - | - |
|  | Licensing services | 300,000 | - | - | - | - | - |
| Lakefront (cap-ture) fisheries development & management | Fisheries co-manage-ment services. | 2,234,695 | - | - | - | - | - |
| Extension sup-ports services | Extension services & support | 1,635,000 | - | - | - | - | - |
| Fish safety & quality assurance | Fish inspection ser-vices | 120,000 | - | - | - | - | - |
|  | Residue monitoring & control services | 130,000 | - | - | - | - | - |
| Blue Economy | Sports fishing & recreation services. | - | - | - | - | - | - |
|  | Cage farming services | - | - | - | - | - | - |
|  | Fish Infrastructure development | - | 4,000,000 | - | - | - | - |
|  | Search & rescue centre services. | - | 4,700,000 | - | - | - | - |
| Sub-Total |  | 244,694,846 | 532,309,271 | 26,303,743 | 22,346,410 | 10.7 | 4.2 |
| Department of Education, Gender inclusivity, Social Services, Youth and Sports |  |  |  |  |  |  |  |
| General Ad-ministration & Support Services | General administration | 278,082,195 |  | 56,103,118 |  | 20.2 | - |
|  | Quality assurance & standard services | 2,006,215 |  |  |  | - | - |
| Early Childhood Development Education Ser-vices | Quality assurance & standard services | 11,500,000 | 44,500,000 | - | - | - | - |
|  | ECDE co-curriculum development | 4,000,000 | - | - | - | - | - |

| Programme | Sub-Programme | Approved Estimates FY 2024/25 |  | Actual Expenditure as of 30 September 2024 |  | Absorption Rate (%) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Recurrent | Development | Recurrent | Develop-ment | Rec | Dev |
|  | School feeding pro-gramme. | 1,250,000 | - | - | - | - | - |
|  | Community ECD services | - | 44,500,000 | - | - |  | - |
| Education sup-port services | Bursary/scholarship | 146,000,000 | - | - | - | - | - |
| Child Care Services | Child protection responsive services & caregiving support services | 1,000,000 | - | - | - | - | - |
| Youth develop-ment & empow-erment | Technical, vocational, education & training | 20,000,000 | 39,500,000 | - | - | - | - |
|  | Youth empowerment program | 5,000,000 |  | - | - | - | - |
|  | Youth enterprise development | 1,000,000 |  | - | - | - | - |
| Sports Develop-ment | Sports Development Services | 36,000,000 | 16,000,000 | - | - | - | - |
|  | Talent development Services | 3,000,000 |  | - | - | - | - |
| Gender Develop-ment & Equality Services | Women Empower-ment | 1,500,000 | - | - | - | - | - |
|  | Gender-responsive education support | 1,250,000 | - | - | - | - | - |
|  | Adolescent Girls & women water, sanitation, & hygiene support services | 1,300,000 | - | - | - | - | - |
|  | People with Disability (PWDs) Empower-ment | 3,000,000 | - | - | - | - | - |
| Culture Devel-opment Promo-tion & Arts | Culture & heritage conservation | 2,950,000 | - | - | - | - | - |
| Sub-Total |  | 518,838,410 | 100,000,000 | 56,103,118 | - | 10.8 | - |
| Medical Services Department |  |  |  |  |  |  |  |
| Planning & Administrative Support Services | Policy formulation, planning, Monitoring & evaluation, Re-search, & learning. | 6,300,000 | - | - | - | - | - |
|  | Administration & support services | 37,300,000 | - | 4,305,600 | - | 11.5 | - |
|  | Human Resource Management & Devel-opment | 1,300,413,949 | - | 273,221,761 | - | 21.0 | - |
|  | Infrastructure & Health Facility Man-agement | - | 212,000,000 |  | 52,755,978 | - | 24.9 |
|  | Health Financing & Universal Health Cov-erage (UHC) co-ordi-nation | 2,460,000 | - | - | - | - | - |
|  | Standards & Quality Assurance | 1,000,000 |  | 200,400 |  | 20.0 | - |

| Programme | Sub-Programme | Approved Estimates FY 2024/25 |  | Actual Expenditure as of 30 September 2024 |  | Absorption Rate (%) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Recurrent | Development | Recurrent | Develop-ment | Rec | Dev |
| Preventive & Promotive Health Services | Environmental health services | 1,200,000 | - | - | - | - | - |
|  | Human Nutrition & Dietetics services | 1,700,000 | - | - | - | - | - |
|  | HIV/AIDS manage-ment | 2,000,000 | - | - | - | - | - |
|  | TB control | 1,200,000 | - | - | - | - | - |
|  | Malaria Control | 1,400,000 | - | - | - | - | - |
|  | Non-Communicable Diseases (NCDs | 1,400,000 | 4,000,000 | - | - | - | - |
|  | Disease surveillance/ Emergency prepared-ness | 950,000 | - | - | - | - | - |
|  | Maternal & Reproduc-tive Health services | 3,160,000 | - | - | - | - | - |
|  | Neonatal, Child, Ado-lescent & Youth health services | 1,800,000 | - | - | - | - | - |
|  | Expanded Program for Immunization (Immu-nization | 3,120,000 | - | - | - | - | - |
|  | Gender-Based Vio-lence health services | 1,200,000 | - | - | - | - | - |
| Donor Funds | Donor Funds | - | 124,723,404 | - | - | - | - |
| Curative, Rehabilitative & Referral Services | Hospital-Level Ser-vices | - | 10,000,000 | - | - | - | - |
|  | Ambulance & Referral Services | 3,200,000 | - | - | - | - | - |
|  | Health Products & Technologies | 74,190,996 | - | - | - | - | - |
|  | Diagnostic & Rehabili-tation Services | 12,580,000 | - | - | - | - | - |
|  | Health Services Man-agement Fund | 136,000,000 | 4,000,000 | - | - | - | - |
| Subtotal |  | 1,592,574,945 | 354,723,404 | 277,727,761 | 52,755,978 | 17.4 | 14.9 |
| Public Health & Sanitation Department |  |  |  |  |  |  |  |
| Planning & Administrative Support Services | Policy formulation, planning, Monitoring & evaluation, Re-search, & learning. | 18,669,591 |  | 1,600,000 |  | 8.6 | - |
|  | Administration & support services | 53,383,200 |  | 1,933,925 |  | 3.6 | - |
|  | Human Resource Management & Devel-opment | 29,754,000 |  | 786,599 |  | 2.6 | - |
|  | Infrastructure & Health Facility Man-agement |  | 200,000,000 |  | 4,556,595 | - | 2.3 |
|  | Health Financing & Universal Health Cov-erage (UHC) co-ordi-nation | 12,000,000 | - | - | - | - | - |
|  | Standards & Quality Assurance | 550,000 | - | - | - | - | - |

| Programme | Sub-Programme | Approved Estimates FY 2024/25 |  | Actual Expenditure as of 30 September 2024 |  | Absorption Rate (%) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Recurrent | Development | Recurrent | Develop-ment | Rec | Dev |
|  | Community health infrastructure services (CHVs) | 30,915,754 | - | - | - | - | - |
| Preventive & Promotive Health Services | Human Nutrition & Dietetics services | 3,850,000 | - | - | - | - | - |
|  | HIV/AIDS manage-ment | 21,170,000 | - | - | - | - | - |
|  | TB control | 8,600,000 | - | - | - | - | - |
|  | Malaria Control | 9,228,000 | - | - | - | - | - |
|  | Non-Communicable Diseases (NCDs | 10,630,000 | - | - | - | - | - |
|  | Disease surveillance/ Emergency prepared-ness | 10,950,000 | - | - | - | - | - |
|  | Health promotion & education | 2,800,000 | - | - | - | - | - |
|  | Maternal & Reproduc-tive Health services | 14,500,000 | - | - | - | - | - |
|  | Neonatal, Child, Ado-lescent & Youth health services | 4,000,000 | - | - | - | - | - |
|  | Expanded Program for Immunization (Immu-nization) | 12,270,000 | - | - | - | - | - |
|  | Gender-Based Vio-lence health services | 900,000 | - | - | - | - | - |
|  | Neglected Tropical Diseases services. | 950,000 | - | - | - | - | - |
|  | Environmental Health & Sanitation Services | 1,000,000 | - | - | - | - | - |
| Curative, Rehabilitative & Referral Services | Health Products & Technologies | 106,255,000 | - | - | - | - | - |
|  | Diagnostic & Rehabili-tation Services | 1,500,000 | - | - | - | - | - |
| Donor Funds | DANIDA | 12,358,500 | - | - | - | - | - |
| Pending Bills | Pending Bills | 2,600,000 | - | - | - | - | - |
|  |  |  |  |  |  | - | - |
| Sub-Total |  | 368,834,045 | 200,000,000 | 4,320,524 | 4,556,595 | 1.2 | 2.3 |
| Department of Environment, Natural Resources, Climate Change & Disaster Management |  |  |  |  |  |  |  |
| General ad-ministration & support services | General administra-tion | 55,689,016 | - | 10,918,678 | - | 19.6 | - |
| Mazingira Youth Programme | Mazingira Youth Pro-gramme | 24,000,000 | - | 2,749,400 | - | 11.5 | - |
| Environment Management & Protection | Solid Waste Manage-ment Services | 17,011,000 | - | 166,401 | - | 1.0 | - |
| Donor Funds | Donor Funds | - | 220,099,573 | - | - | - | - |
| Climate Change Adaptation & Mitigation | Climate Change | 16,500,000 | - | - | - | - | - |
|  | Climate Information Services (CIS) | 500,000 | - | - | - | - | - |

| Programme | Sub-Programme | Approved Estimates FY 2024/25 |  | Actual Expenditure as of 30 September 2024 |  | Absorption Rate (%) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Recurrent | Development | Recurrent | Develop-ment | Rec | Dev |
|  | Climate Change legal frameworks | 4,500,000 | - | - | - | - | - |
|  | Establish Grievance Redress Structures | 10,700,000 | - | - | - | - | - |
|  | Strengthening Re-source Management Units (CFAs and WRUAs) | 5,000,000 | - | - | - | - | - |
|  | Climate Change Awareness Campaigns | 10,500,000 | - | - | - | - | - |
|  | Climate Change Gov-ernance | 10,500,000 | - | - | - | - | - |
|  | Facilitation of Climate change Operations | 9,820,000 | - | - | - | - | - |
|  | Monitoring and Evaluation of FLLoCA Projects | 5,900,000 | - | - | - | - | - |
|  | FLLoCA PIU consulta-tive meetings | 4,700,000 | - | - | - | - | - |
|  | Support climate change learning events and exhibition | 5,200,000 | - | - | - | - | - |
| Natural Resourc-es Management & Forestry Development | Forestry development | 5,800,000 | - | - | - | - | - |
|  | Natural Resources Management & Con-servation | 3,200,000 | - | - | - | - | - |
|  | Artisanal mining & quarry services | 500,000 | - | - | - | - | - |
| Pending Bills | Pending Bills | - | 45,000,000 | - | - | - | - |
| Disaster Man-agement and Response | Disaster Management | 10,700,000 | - | - | - | - | - |
|  | Fire Rescue Services | 2,800,000 | - | - | - | - | - |
|  | - | - | - | - | - | - | - |
| Sub-Total |  | 203,520,016 | 265,099,573 | 13,834,479 | - | 6.8 | - |
| Department of Finance & Economic Planning |  |  |  |  |  |  |  |
| General ad-ministration & support services | Administrative ser-vices (Accounts) | 505,522,722 | - | 44,595,812 | - | 8.8 | - |
|  | Administrative ser-vices (Supply Chain) | 16,020,000 | - | 2,490,500 | - | 15.5 | - |
|  | Administrative ser-vices (Planning) | 42,856,562 | 3,500,000 | 7,040,505 | - | 16.4 | - |
| Finance & Accounting services. | Accounting services | 183,673,087 | - | 48,776,446 | - | 26.6 | - |
| Resource Mobili-sation services | Revenue mobilisation services | 47,685,000 | - | 459,000 | - | 1.0 | - |
|  | Revenue board ser-vices | 17,115,000 | - |  | - | - | - |
| Supply chain management services | Supply chain manage-ment Services | 4,419,295 | 16,500,000 | 711,200 | 4,646,990 | 16.1 | 28.2 |
| Audit services | Audit services | 46,118,326 | - | 5,479,550 | - | 11.9 | - |
|  | Internal Audit Com-mittee | 4,600,000 | - |  | - | - | - |

| Programme | Sub-Programme | Approved Estimates FY 2024/25 |  | Actual Expenditure as of 30 September 2024 |  | Absorption Rate (%) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Recurrent | Development | Recurrent | Develop-ment | Rec | Dev |
| Economic Plan-ning Services | Policy plans & formu-lation | 18,000,000 | - | 5,884,495 | - | 32.7 | - |
| Budgeting Ser-vices | Budget co-ordination & management | 63,496,061 | - | 2,509,500 | - | 4.0 | - |
| County Statisti-cal Information Services | County statistical information system | 8,500,000 | - | - | - | - | - |
| County Budget & Economic Forum Services | County budget & eco-nomic forum services | 7,000,000 | - | - | - | - | - |
| Sub-Total |  | 965,006,053 | 20,000,000 | 117,947,008 | 4,646,990 | 12.2 | 23.2 |
| Department of Lands, Physical Planning, Housing & Urban Development |  |  |  |  |  |  |  |
| Administrative Services | General administrative services | 83,926,592 | - | 8,739,393 | - | 10.4 | - |
|  | General administra-tive services (Physical Planning) | 16,334,756 | - | - | - | - | - |
| Land, Rent & Rates Services | Rents & rates services | - | 15,000,000 | - | - | - | - |
| Land Survey Services | Land Survey Services | - | 5,000,000 | - | - | - | - |
| Physical Plan-ning Services | Physical Planning Services | 5,800,000 | - | - | - | - | - |
|  | Preparation Of Special area Plan-Phase I |  | 8,000,000 | - | - | - | - |
|  | Preparation of town plans | - | 24,000,000 | - | - | - | - |
|  | Completion of GIS lab | - | 4,000,000 | - | - | - | - |
|  | Maintenance and civil works | - | 4,000,000 | - | - | - | - |
|  | Physical Planning Ser-vices (Establishment of County Physical and Land Use Planning Consultative Forum and Liaison Commit-tee) | 1,308,000 | - | - | - | - | - |
| External Fund-ing | External Funding | - | 35,000,000 | - | - | - | - |
| Urban Develop-ment Services | Urban Development Services | 1,557,244 |  | - | - | - | - |
| Sub-Total |  | 108,926,592 | 95,000,000 | 8,739,393 | - | 8.0 | - |
| Rongo Municipality |  |  |  |  |  |  |  |
| Administrative and Support Services | Planning, Adminis-tration, & governance services | 13,280,000 |  |  |  | - | - |
|  | Board Activities | 6,720,000 |  |  |  | - | - |
| Infrastructure Development | Infrastructure devel-opment |  | 26,800,000 |  |  | - | - |
| Sub-Total |  | 20,000,000 | 26,800,000 | - | - | - | - |
| Kehancha Municipality |  |  |  |  |  |  |  |

| Programme | Sub-Programme | Approved Estimates FY 2024/25 |  | Actual Expenditure as of 30 September 2024 |  | Absorption Rate (%) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Recurrent | Development | Recurrent | Develop-ment | Rec | Dev |
| Administrative and Support Services | Planning, Adminis-tration, & governance services | 14,280,000 |  |  |  | - | - |
|  | Board Activities | 6,720,000 |  |  |  | - | - |
| Infrastructure Development | Infrastructure devel-opment |  | 26,800,000 |  | 4,391,020 | - | 16.4 |
| Sub-Total |  | 21,000,000 | 26,800,000 | - | 4,391,020 | - | 16.4 |
| Migori Municipality |  |  |  |  |  |  |  |
| Administrative and Support Services | Planning, Adminis-tration, & governance services | 13,280,000 |  | - |  | - | - |
|  | Board Activities | 6,720,000 |  |  |  | - | - |
| Infrastructure Development | Infrastructure devel-opment |  | 64,181,008 |  |  | - | - |
| Sub-Total |  | 20,000,000 | 64,181,008 |  |  | - | - |
| Awendo Municipality |  |  |  |  |  |  |  |
| Administrative and Support Services | Planning, Adminis-tration, & governance services | 13,280,000 |  |  |  | - | - |
|  | Board Activities | 6,720,000 |  |  |  | - | - |
| Infrastructure Development | Infrastructure devel-opment |  | 26,800,000 |  |  | - | - |
| Sub-Total |  | 20,000,000 | 26,800,000 | - | - | - | - |
| Department of Roads, Transport, Public Works & Infrastructural Development |  |  |  |  |  |  |  |
| General ad-ministration & support services | Administrative services | 124,724,552 |  | 10,148,939 |  | 8.1 | - |
|  | Administrative services | 17,779,182 |  |  |  | - | - |
| Road De-velopment, Maintenance & Management | Mechanisation service |  |  |  |  | - | - |
|  | Community access roads |  | 150,000,000 |  | 8,697,739 | - | 5.8 |
|  | Major roads |  | 444,000,000 |  |  | - | - |
|  | Bridges & culvert services |  | 50,000,000 |  | 37,604,829 | - | 75.2 |
|  | Other Infrastructure |  | - | - | - | - | - |
|  | Road Maintenance Fuel Roads |  | 100,000,000 | - | - | - | - |
| Transport Infrastructure Management Services | Transport management services |  | 26,000,000 | - | - | - | - |
| Public works services | Architectural Services | 2,240,000 |  | - | - | - | - |
|  | Quantity Surveyor’s Services | 1,660,000 |  | - | - | - | - |
|  | Mechanical & Electrical Engineering services | 1,340,000 |  | - | - | - | - |
|  | Structural engineering services | 1,916,000 |  | - | - | - | - |
|  | Building & construction services. | - |  | - | - | - | - |

| Programme | Sub-Programme | Approved Estimates FY 2024/25 |  | Actual Expenditure as of 30 September 2024 |  | Absorption Rate (%) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Recurrent | Development | Recurrent | Develop-ment | Rec | Dev |
|  | Mechanisation service | 720,000 |  | - | - | - | - |
| Sub-Total |  | 150,379,734 | 770,000,000 | 10,148,939 | 46,302,568 | 6.7 | 6.0 |
| Department of Trade, Tourism, Industry, Market & Co-operative Development |  |  |  |  |  |  |  |
| Policy, Planning & administrative support services | Administrative support services | 118,306,968 | - | 11,056,016 |  | 9.3 | - |
|  | Administrative support services (Co-operatives | 3,100,000 |  |  |  | - | - |
| Trade Promo-tion, Develop-ment & Support to SMEs | Trade development & promotion of SME services | 2,000,000 |  |  |  | - | - |
|  | Trade infrastructure development services | - | 80,000,000 |  | 15,964,035 | - | 20.0 |
|  | Trade regulation & information management systems | 4,000,000 |  |  |  | - | - |
|  | Community projects | - |  |  |  | - | - |
| Legal metrology services | Legal metrology services | 4,800,000 |  |  |  | - | - |
| Industrial development & investment services | Industrial & enterprise development | 3,700,000 | 250,000,000 | - | - | - | - |
|  | Investment promotion services. | 2,300,000 | - | - | - | - | - |
| Tourism Research & Development | Tourism product development | 5,400,000 | - | - | - | - | - |
|  | Tourism promotion, investment & marketing | 3,600,000 | - | - | - | - | - |
|  | Tourism development & investment services. | - | - | - | - | - | - |
| Co-operative Policy, Research Advisory | Co-operative Policy, Research Advisory | 3,000,000 | - | - | - | - | - |
| Co-operative Development & Promotion Services | Co-operative Development & Promotion Services | 2,400,000 | - | - | - | - | - |
| Co-operative Audit | Co-operative Audit | 1,100,000 | - | - | - | - | - |
| Co-operative Governance, Oversight & Compliance | Co-operative Governance, Oversight and Compliance | 400,000 | - | - | - | - | - |
| Liquor Licensing and Control | Liquor Licensing and Control | 2,000,000 | - | - | - | - | - |
| Sub-Total |  | 156,106,968 | 330,000,000 | 11,056,016 | 15,964,035 | 7.1 | 4.8 |
| County Assembly Entity |  |  |  |  |  |  |  |
| General ad-ministration & support services | Administrative services | 747,178,947 |  | 72,954,512 |  | 9.8 | - |
|  | Administrative services | 28,789,750 |  | - |  | - | - |
| Infrastructure Development | Infrastructure Development services |  | 50,000,000 |  |  | - | - |

| Programme | Sub-Programme | Approved Estimates FY 2024/25 |  | Actual Expenditure as of 30 September 2024 |  | Absorption Rate (%) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Recurrent | Development | Recurrent | Develop-ment | Rec | Dev |
| Pending Bills | Pending Bills | 20,000,000 |  |  |  | - | - |
| Oversight Management Services | Committee Management Services | 125,188,740 |  | 3,754,339 |  | 3.0 | - |
|  | Representation | 66,314,772 |  | 12,223,131 |  | 18.4 | - |
| Sub-Total |  | 987,472,209 | 50,000,000 | 88,931,982 | - | 9.0 | - |
| Department of Water and Energy |  |  |  |  |  |  |  |
| Policy, General Administration & Support Services | General administrative services | 106,019,266 |  | 2,742,138 | - | 2.6 | - |
|  | Operation & maintenance of rural water services | 799,000 |  |  | - | - | - |
| Water supply & Management services | Urban Water Supply & sewerage services | 23,000,000 | 20,831,998 | 10,307,980 | - | 44.8 | - |
|  | Rural Water Services | 3,979,668 |  |  | - | - | - |
|  | Water Conservation, protection, & Governance |  | 5,200,000 |  | - | - | - |
|  | Community water services |  | 100,000,000 |  | - | - | - |
| Pending Bills | Pending Bills |  | 53,968,002 |  | 19,603,215 | - | 36.3 |
| External Funding | Donor Funding |  | 199,874,000 |  |  | - | - |
| Energy Develop-ment Services | Renewable energy development | 15,750,000 | 20,000,000 |  |  | - | - |
| Sub-Total |  | 149,547,934 | 399,874,000 | 13,050,118 | 19,603,215 | 8.7 | 4.9 |
| Grand- Total |  | 6,945,304,608 | 3,441,587,256 | 719,288,683 | 172,066,772 | 10.4 | 5.0 |

Source: Migori County Treasury

Based on absorption rates, the sub-programmes with the highest implementation levels were Crop Develop-ment in the Department of Agriculture, Livestock, Veterinary Services, Fisheries & Blue Economy, at 87 per cent, followed by Market Support Infrastructure, at 85 per cent.

### Accounts Operated in Commercial Banks

The County government operated 76 accounts with commercial banks, of which 29 were for County Hospitals.

This is contrary to Regulations 82(1)(b) of the PFM (County Governments) Regulations, 2015, which requires that County government bank accounts be opened and maintained at the Central Bank of Kenya. The only ex-emption is for imprest bank accounts for petty cash and revenue collection bank accounts.

### Key Observations and Recommendations

In the course of overseeing and reporting on the implementation of the County budget, the COB identified the following challenges which hampered effective budget implementation;

- The underperformance of own-source revenue at Kshs.101.82 million against an annual target of Kshs.620 million, representing 16.4 per cent of the yearly target.

- The County Treasury did not properly manage the inter-departmental vote books and had weak budgeting practices, as shown in Table 3.181. The county departments incurred expenditures over approved exche-quer issues and diverted funds.

- There was a high level of pending bills, which amounted to Kshs.1.76 billion as of 30 September 2024. Further, the County Treasury did not adhere to the payment plan for the pending bills.

- High wage bills which accounted for 37 per cent of the County total revenue in FY 2024/25 in the report-ing period of Kshs.1.56 billion, which is above the ceiling provided by law.

- The County Government uses commercial bank accounts for operations contrary to Regulations 82(1)

(b) of the PFM (County Governments) Regulations, 2015, which requires that County Government bank accounts be opened and maintained at the Central Bank of Kenya. The commercial bank accounts are mainly for County Health facilities & Dispensaries Services and various departments’ office operations and activities.

The County should implement the following recommendations to improve budget execution:

  - The County should address its own-source revenue performance to ensure the approved budget is fully financed. Appropriate austerity measures should be implemented to ensure expenditure commitments are aligned with available revenue.

  - The County Treasury should improve the Vote book and budgetary controls to ensure expenditure is within the approved budget and exchequer releases.

  - The County Leadership should develop strategies to ensure the wage bill is within the legal limit of 35 per cent of total revenue as provided under Regulation 25 (1) (b) of the Public Finance Management (County Governments) Regulations, 2015

  - The County leadership should address the situation of pending bills to ensure that genuine bills are paid promptly in the remaining financial year. Further, compliance with the payment plan should be enforced.

  - The County Government should ensure that bank accounts are opened and operated at the Central Bank of Kenya as the law requires. However, imprest bank accounts for petty cash and revenue collection ac-counts are exempted.