REPUBLIC OF KENYA

MIGORI COUNTY

BUDGET REVIEW AND OUTLOOK PAPER

FY 2024/2025

October, 2025

Table of Contents

LIST OF TABLES.	iii

FOREWORD	iv

ACKNOWLEDGEMENT	vi

SECTION ONE: INTRODUCTION	7

1.1 OBJECTIVES OF CBROP	7

1.2 SIGNIFICANCE OF CBROP	7

1.3 STRUCTURE OF CBROP	7

1.4 Legal Basis for the Publication of the County Budget Review and outlook paper	8

SECTION TWO: REVIEW OF FISCAL PERFORMANCE IN 2024/2025	9

2.1 Fiscal Performance of FY 2024/25 Budget	9

2.2 Actual Revenue Analysis.	11

2.2.1 Equitable Share	13

2.2.2 Conditional Grants/Donor Funds	14

2.2.3 Own Source Revenue	15

2.3 Exchequer Releases and Returned Issue	17

2.4 Overall Expenditure Review	18

2.4.2 Analysis of Recurrent Expenditure	19

2.4.2.1 Compensation of employees	19

2.4.2.2 Operations and Maintenance (Use of Goods and Services)	20

2.4.2.3 Facility Improvement Financing	20

2.4.3 Development Expenditure Analysis.	21

2.4.3.1 Departments Expenditure Overview	21

2.5 Implication of Fiscal Performance for the FY 2024/25 in relation to Financial Objectives	22

2.6 Fiscal Responsibility Principles	23

2.8 Non-financial performance.	24

SECTION THREE: RECENT ECONOMIC OUTLOOK	26

3.1 Macroeconomic and Financial Developments	26

3.2 Domestic Economic Growth Outlook	26

3.2.1 County Economic Outlook for FY 2025/2026	26

3.2.2	County Medium-Term Priorities	26

3.2.3 Capital Development Projects	27

3.3 Risks to the Economic Outlook	30

3.4 Mitigation Measures	30

SECTION FOUR: RESOURCE ALLOCATION FRAMEWORK	32

SECTION FIVE: CONCLUSION	37

ANNEX 1: SCHEDULE FOR PUBLIC PARTICIPATION	38

ANNEX 2: KEY ACHIEVEMENTS	39

2.3.2.1 Agriculture, Livestock, veterinary services, fisheries and blue economy	39

Livestock production	39

Veterinary services	39

Fisheries and Blue Economy	40

2.3.2.3 Education, gender Inclusivity, Social services, Youth and Sports.	40

2.3.2.4 Environment, Natural resources, climate change and disaster management	41

2.3.2.6 Health services and Sanitation	41

2.3.2.7 Lands, housing, Physical planning and Urban Development.	43

2.3.2.8 Rongo Municipality	44

2.3.2.9Awendo Municipality.	44

2.3.2.10 Kehancha Municipality	44

2.3.2.11 Migori Municipality	45

2.3.2.12 Office of the Governor	45

2.3.2.15Roads, transport, public works and Infrastructural Development.	46

2.3.2.16 Trade Tourism, Industry,market and cooperative Development.	47

2.3.2.17 Water and Energy	49

# LIST OF TABLES.

Table 1: Annual Budget allocation against the Actual Receipts	8

Table 2: Analysis of revenue receipts for FY 2023/24	11

Table 3: Comparison of budget against actual receipts of the revenue streams for the FYs 2023/24 and 2024/25	11

Table 4: Conditional/ Donor Funds Budgeted Against Actual Receipts for FY 2024/25	13

Table 5: The top 5 performing revenue streams for the FY 2023/24	15

Table 6: Exchequer release as a percentage of the total revenue received	16

Table 7: Total Exchequer Issues in   FY 2024/25	16

Table 8: Summary of Budgeted Versus Actual Expenditure by Economic Classification for FY 2024/25	17

Table 9: Expenditure analysis by economic classification	18

Table 10: Migori County Health Facilities Expenditure Performance in FY 2024/25	19

Table 11: Analysis of budget performance by department	20

Table 12: Fiscal Projections	32

Table 13: Fiscal Projections for FY 2026/27 by Sector	33

# FOREWORD

The County Budget Review and Outlook Paper (CBROP) for the Financial Year 2024/25 is prepared pursuant to Section 118 of the Public Finance Management (PFM) Act, 2012 and the PFM (County Governments) Regulations, 2015. This statutory document provides a detailed review of the County’s fiscal performance for FY 2024/25 against budgetary allocations, assesses recent macroeconomic developments, and outlines the fiscal outlook that will inform the preparation of the County Fiscal Strategy Paper (CFSP) 2026 and the subsequent budget for FY 2026/27.

The CBROP is published at a time when the County Government of Migori continues to navigate a constrained fiscal environment characterized by revenue shortfalls, delayed disbursement of conditional grants, and rising expenditure pressures. Despite these challenges, the County has made significant strides in enhancing Own Source Revenue (OSR) collection, improving budget absorption, and implementing priority programmes aligned with the County Integrated Development Plan (CIDP III) and the Fourth Medium Term Plan.

The fiscal performance for FY 2024/25 reflects broad compliance with the fiscal responsibility principles outlined in the PFM Act, including maintaining recurrent expenditure within total revenue, allocating at least 30 percent of the budget to development programmes, and keeping the wage bill within the prescribed threshold. The County Government remains committed to sustaining fiscal discipline, strengthening revenue administration, and prioritizing high-impact interventions that promote inclusive growth and service delivery.

As we embark on the preparation of the FY 2026/27 budget and the Medium-Term Expenditure Framework (MTEF), this CBROP provides the necessary baseline for resource allocation decisions. Sector Working Groups (SWGs) are urged to align their budget proposals with the priorities outlined herein, ensuring that all expenditures are justified and contribute to the County’s strategic development agenda.

Finally, we reaffirm our commitment to transparency, accountability, and inclusive development. The insights and recommendations contained in this CBROP will guide the formulation of the County Fiscal Strategy Paper (CFSP) 2026 and the subsequent budget for FY 2026/27.

Maurice Otunga

CECM – Finance & Economic Planning

# ACKNOWLEDGEMENT

The preparation of the County Budget Review and Outlook Paper (CBROP) for the Financial Year 2024/25 marks a significant milestone in the County’s commitment to prudent financial management and evidence-based planning. This document has been developed in accordance with the provisions of the Public Finance Management (PFM) Act, 2012 and the PFM (County Governments) Regulations, 2015.

The successful completion of this CBROP was made possible through the collaborative efforts of various stakeholders. We extend our sincere appreciation to all County Departments and Sector Working Groups (SWGs) for their timely submission of budget execution reports and provision of relevant data and insights. Their contributions were instrumental in compiling the fiscal performance review and shaping the medium-term outlook.

We acknowledge the technical team within the Department of Finance and Economic Planning for their dedication in consolidating, analyzing, and aligning the document with statutory requirements and policy priorities. Special thanks go to the County Assembly for its oversight role and to the Controller of Budget for providing exchequer release data that informed the expenditure analysis. We are also grateful to development partners and the public for their valuable input during the consultative forums held across all sub-counties. Their feedback enriched the document and ensured that the fiscal strategy reflects the aspirations and needs of Migori County residents.

I wish to thank all departments, entities, and stakeholders who contributed to the preparation of this document. Your continued support and collaboration remain critical in advancing the County’s fiscal and development objectives.

Dr. Achuora John Odoyo
Chief Officer – Finance and Economic Planning

# SECTION ONE: INTRODUCTION

This County Budget Review and Outlook Paper (CBROP) for FY 2024/25 is prepared in accordance with Section 118 of the Public Finance Management (PFM) Act, 2012 and the PFM (County Governments) Regulations, 2015. It presents a review of the actual fiscal performance for FY 2024/25 against budgetary allocations, assesses recent economic developments, and outlines implications for the fiscal outlook as set out in the County Fiscal Strategy Paper (CFSP) 2025.

## 1.1 OBJECTIVES OF CBROP

The 2025 CBROP provides a review of the FY 2024/2025 fiscal and non-fiscal performance and their impact on the financial objectives and fiscal responsibilities set out in the CFSP prepared in line with the budget policy statement. The 2025 CBROP provides indicative ceilings which will guide the budget preparation process for the FY 2026/2027

## 1.2 SIGNIFICANCE OF CBROP

The CBROP is a key policy document that links planning with budgeting. It plays a critical role in the budget-making process within the MTEF framework by reviewing fiscal performance for the FY 2024/25 and identifying deviations from the budget. This enables the County Government to make realistic forecasts for the upcoming fiscal year.

## 1.3 STRUCTURE OF CBROP

The paper is organized into five sections:

- Section I: Introduction and objectives of CBROP;

- Section II: Review of fiscal performance in FY 2024/25, subdivided into: overview of the budget, revenue analysis, and overall expenditure review;

- Section III: Recent economic developments and updated macroeconomic outlook, including: macroeconomic trends, domestic growth outlook, and risks;

- Section IV: Resource allocation framework, including revenue and expenditure projections for FY 2026/27 and the medium term;

- Section V: Conclusion, highlighting the purpose and next steps.

## 1.4 Legal Basis for the Publication of the County Budget Review and outlook paper

The County Budget Review and Outlook Paper is prepared in accordance with Section 118 of the Public Financial Management Act, 2012. The law states that:

1.   The County Treasury shall prepare and submit to County Executive committee for approval, by 30th September in each financial year, a County Budget Review and Outlook Paper which shall include:

a)   Actual fiscal performance in the previous financial year compared to the budget appropriation for that year;

b)  Updated economic and financial forecasts with sufficient information to show changes from the forecasts in the most recent County Fiscal strategy paper

c)   Information on how actual financial performance for the previous financial year may have affected compliance with the fiscal responsibility principles or the financial objectives in the latest County Fiscal strategy paper; and

d)  The    reasons    for    any    deviation    from    the    financial    objectives    together with proposals to address the deviation and the time estimated to do so.

2. County Executive committee shall consider the County Budget Review and outlook Paper with a view to approving it with or without amendments, not later than fourteen days after its submission.

3.  Not later than seven days after the CBROP has been approved by Executive committee, the County Treasury shall:

a)   Submit the paper to the Budget and appropriation    Committee of the County Assembly to be laid before the County assembly; and

b)  Publish and publicise the paper not later than fifteen days after laying the Paper before County Assembly.

Fiscal Responsibility Principles in the Public Financial Management Law

In line with the Constitution, the new Public Financial Management (PFM) Act, 2012, sets   out   the   fiscal   responsibility   principles   to   ensure   prudency   and transparency in the management of public resources.  The PFM law (Section 107(b)) states that:

1)  The county government’s recurrent expenditure shall not exceed the county government’s total revenue

2)  Over the medium term, a minimum of 30% of the County budget shall be allocated to development expenditure

3)  The County government’s expenditure on wages and benefits for public officers shall not exceed a percentage of the County government revenue as prescribed by the regulations.

4)  Over the medium term, the County government’s borrowings shall be used only for the purpose of financing development expenditure and not for recurrent expenditure.

5)  Public debt and obligations shall be maintained at a sustainable level as approved by County Government (CG)

6)  Fiscal risks shall be managed prudently

7)  A reasonable degree of predictability with respect to the level of tax rates and tax bases shall be maintained, taking into account any tax reforms that may be made in the future on

# SECTION TWO: REVIEW OF FISCAL PERFORMANCE IN 2024/2025

## 2.1 Fiscal Performance of FY 2024/25 Budget

During the period under review, the County Government of Migori operated under an approved supplementary budget of Kshs. 12.147 billion, comprising Kshs. 7.68 billion (63.2%) for recurrent expenditure and Kshs. 4.466 billion (36.8%) for development programmes. This represented a 5.87 percent increase from the previous financial year’s supplementary budget of Kshs. 11.473 billion.

The budget was expected to be financed through various revenue streams, including Kshs. 8.385 billion (69.0%) from the equitable share of revenue raised nationally, Kshs. 688.425 million (5.7%) as unspent balances carried forward from FY 2023/24, Kshs. 2.27 billion (18.7%) from conditional grants and donor funding, and Kshs. 800 million (6.6%) from own source revenue. The own source revenue comprised Kshs. 250 million from the Facility Improvement Fund (FIF) and Kshs. 550 million from ordinary revenue sources, accounting for 31.2 percent and 68.8 percent of total OSR respectively.

A detailed breakdown of the annual budget allocations against actual receipts is presented in table 1 below. Overall, the County realized 86.5 percent of the total annual budget allocation during the reporting period.

Table 1: Annual Budget allocation against the Actual Receipts

| S/No. | Revenue Category | Annual Budget Allocation (Kshs) | Actual Receipts (Kshs.) | Actual Receipts as Percentage of Annual Budget Allocation (%) |
| --- | --- | --- | --- | --- |
| A | Equitable Share of Revenue Raised Nationally - | 8,385,079,399 | 8,385,076,709 | 100 |
| Sub-total |  | 8,385,079,399 | 8,385,076,709 | 100 |
| B | Donor Funds/Conditional Grants |  |  |  |
| 1. | DANIDA Grant (Universal Healthcare in Devolved System Program) | 12,358,500 | 10,432,500 | 84 .4 |
| 2. | IDA (World Bank) Credit for National Agricultural and Rural Inclusive Growth Project (NARIGP) | 5,000,000 | - | - |
| 3. | EU Grant for Instrument for Devolution Advice and Support (IDEAS) | 5,706,628 | - | - |
| 4. | Sweden - Agricultural Sector Development Support Programme (ASDSP) II | 1,120,452 | - | - |
| 5. | KABDP Sida | 10,918,919 | - | - |
| 6. | KABDP MOA&LD (GoK) | 1,000,000 | - | - |
| 7. | Aquaculture Business Development Project (ABDP) | 13,617,785 | - | - |
| 8. | Livestock Value Chain Support Project | 14,323,680 | - | - |
| 9. | Climate Change - German Dev't Bank (KfW) - (FLLoCA -CCRI Grant) | 390,000,000 | 16,968,438 | 4.4% |
| 10. | Climate Change - IDA World Bank (FLLoCA) | 11,000,000 | 11,000,000 | 100 |
| 11. | Urban Institutional Grant (UIG) | 35,000,000 | 32,309,300 | 92.3% |
| 12. | Migori Municipality URB Dvt Grant | 54,181,008 | - | - |
| 13. | Awendo Municipality URB Dvt Grant | 16,800,000 | - | - |
| 14. | Rongo Municipality URB Dvt Grant | 16,800,000 | - | - |
| 15. | Kehancha Municipality URB Dvt Grant | 16,800,000 | - | - |
| 16. | Grant from National Government - Industrial Park | 250,000,000 | 54,131,579 | 21.7 |
| 17. | Kenya Water and Sanitation (K-WASH) Program | 199,874,000 | - | - |
| 18. | National Agricultural Value Chain Development Project (NAVCDP) | 250,000,000 | 71,537,277 | 28.6 |
| 19. | Kenya Devolution Support Program II | 37,500,000 | - | - |
| 21. | Leasing of Medical Equipment | 124,723,404 | - | - |
| 22. | Fertilizer Subsidy | 144,621,807 | - | - |
| 23. | Allocation for Court fines | 974,165 | - | - |
| 24. | Allocation for Mineral Royalties | 3,125,408 | - | - |
| 25. | Basic Salary arrears for County Government Health Workers | 27,687,815 | - | - |
| 26. | Community Health Promoters (CHPs) Projects | 88,380,000 | - | - |
| 27. | MIGORI COUNTY CLIMATE CHANGE FUND FLOCCA Balances C/Fwd | 372,833,613 | 372,833,613 | 100 |
| 28. | MIGORI COUNTY HEALTH SPECIAL Balances C/Fwd | 915,068 | 915,068 | 100 |
| 29. | MIGORI COUNTY RMLF Balances C/Fwd | 681,918 | 681,918 | 100 |
| 30. | MIGORI COUNTY NARIGP OPERATIONS ACCOUNT Bal. C/Fwd | 4,261,826 | 4,261,826 |  |
| 31. | MIGORI COUNTY AGRICULTURE CHAIN Balances C/Fwd | 161,794,532 | 161,794,532 |  |
| 32. | MIGORI COUNTY INDUSTRIAL PARK Balances C/Fwd | 1,500,000 | 1,500,000 | 100 |
| Sub-total |  | 2,273,500,528 | 738,366,051 | 32.5 |
| C | Own Source Revenue |  |  |  |
| 33. | Ordinary Own Source Revenue | 550,000,000 | 337,363,187 | 61.3 |
| 34. | Appropriation in Aid (A-I-A) | - | - |  |
| 35. | Facility Improvement Fund (FIF) | 250,000,000 | 354,192,398 | 141.7 |
| Sub-total |  | 800,000,000 | 691,555,585 | 86.4 |
| D | Other Sources of Revenue |  |  |  |
| 36. | Unspent balance from FY 2023/24 | 688,425,652 | 688,425,652 | 100 |
| 37. | Other Revenues (provide a list) | - | - | - |
| Sub-Total |  | 688,425,652 | 688,425,652 | 100 |
| Grand Total |  | 12,147,005,579 | 10,503,423,997 | 86.5 |

The pie chart below shows the contribution of the various revenue categories to the overall budget with Equitable share contributing 69% of the total budget for the FY 2024/25. The donor funds and grants contributed 19% while own source revenue and the unspent balances from the previous financial year each contributed 6% to the overall budget.

Figure 1: Revenue sources contribution to FY 2024/25 budget

## 2.2 Actual Revenue Analysis.

During the period under review, total actual revenue received amounted to Kshs. 10.503 billion, against the revised budget of Kshs. 12.147 billion, representing an overall realization rate of 86.5 percent. The revenue comprised Kshs. 8.385 billion from the equitable share of revenue raised nationally, reflecting a full realization of the projected amount; Kshs. 691.56 million, representing 86.4 percent of the targeted own source revenue; Kshs. 738.37 million, accounting for 32.5 percent of the expected conditional grants and donor funds; and Kshs. 688.43 million, being the full realization of returned issues from the previous financial year’s unspent balances. A detailed analysis of the revenue receipts is presented in Table 2 below

Table 2: Analysis of revenue receipts for FY 2023/24

| Revenue Category | Annual Budget Allocation (Kshs) | Actual Receipts (Kshs.) | Actual Receipts as Percentage of Annual Budget Allocation (%) |
| --- | --- | --- | --- |
| Balance c/f | 688,425,652.00 | 688,425,652.00 | 100.0 |
| Equitable Share of Revenue Raised Nationally | 8,385,079,399.00 | 8,385,076,709.00 | 100.0 |
| Additional Allocations (Grants, Donor funds etc) | 2,273,500,528.00 | 738,366,050.90 | 32.5 |
| Own Source Revenue | 800,000,000.00 | 691,555,585.15 | 86.4 |
| Grand Total | 12,147,005,579.00 | 10,503,423,997.05 | 86.5 |

Overall, the total revenue received during the period under review increased by 8.3% compared to the previous financial year 2023/24 amount of Kshs 9,697,350,634 as shown in table 3 below. This performance reflects a positive trajectory in revenue mobilization, particularly in OSR and donor funding, despite challenges in full disbursement of external resources. The County’s efforts in automation, digitization, and enforcement have significantly contributed to improved own source revenue collection.

Table 3: Comparison of budget against actual receipts of the revenue streams for the FYs 2023/24 and 2024/25

| Revenue | 2023/24 FY |  | 2024/25 FY |  | Variance of the Actual Receipts | % Variance |
| --- | --- | --- | --- | --- | --- | --- |
|  | Budget (Kshs) (A1) | ACTUAL (KSHS) (A2) | Budget (Kshs) (B1) | ACTUAL (Kshs) (B2) | (B2-A2) |  |
| Equitable Share | 8,341,446,108 | 7,674,130,419 | 8,385,079,399.00 | 8,385,076,709.00 | 710,946,290.00 | 9.3% |
| Local Revenue | 625,474,299 | 512,566,310 | 800,000,000.00 | 691,555,585.15 | 178,989,275.15 | 34.9% |
| Other Receipts (donor funds, conditional grants etc.) | 1,521,148,858 | 525,685,649 | 2,273,500,528.00 | 738,366,050.90 | 212,680,401.90 | 40.5% |
| Total | 10,488,069,265 | 9,697,350,634 | 12,147,005,579.00 | 10,503,423,997.05 | 806,073,363.05 | 8.3% |

The figure below shows the comparison of revenue received in the FY 2023/2024 and FY 2024/2025.From the figure there was an increment in revenue receipts in the FY 2023/2024 as compared to FY 2024/2025

Figure 2: Comparison of revenue receipts FY 2022/2023 versus FY 2023/2024

### 2.2.1 Equitable Share

In FY2024/25, the County Government received Kshs. 8,385,076,709 as equitable share of the revenue raised nationally representing 69% of the total revenue received. This was an increase of Kshs. 710,946,290.00 from the amount received during 2023/24 FY (Kshs 7,674,130,419) representing a 9.3% increase as shown in figure 3 below.

Figure 3: Comparison of Equitable share receipts for FY 2023/2024 versus FY 2024/2025:

### 2.2.2 Conditional Grants/Donor Funds

During the reporting period, the County Government of Migori anticipated receipts amounting to Kshs. 2,273,500,528 from conditional grants and donor funding. However, actual disbursements under this category amounted to Kshs. 738,366,051, translating to a realization rate of 32.5 percent. Despite the shortfall against the projected target, the amount received reflects a notable improvement of Kshs. 210,680,402 or 40.1 percent compared to the previous financial year’s actual receipts of Kshs. 525,685,649. This performance underscores the need for enhanced coordination with development partners to ensure timely disbursement of earmarked resources and improve budget execution in subsequent periods.

Table 4: Conditional/ Donor Funds Budgeted Against Actual Receipts for FY 2024/25

| S/No. | Revenue Category | Annual Budget Allocation (Kshs) | Actual Receipts (Kshs.) |
| --- | --- | --- | --- |
| 1. | DANIDA Grant (Universal Healthcare in Devolved System Program) | 12,358,500 | 10,432,500 |
| 2. | IDA (World Bank) Credit for National Agricultural and Rural Inclusive Growth Project (NARIGP) | 5,000,000 | - |
| 3. | EU Grant for Instrument for Devolution Advice and Support (IDEAS) | 5,706,628 | - |
| 4. | Sweden - Agricultural Sector Development Support Programme (ASDSP) II | 1,120,452 | - |
| 5. | KABDP Sida | 10,918,919 | - |
| 6. | KABDP MOA&LD (GoK) | 1,000,000 | - |
| 7. | Aquaculture Business Development Project (ABDP) | 13,617,785 | - |
| 8. | Livestock Value Chain Support Project | 14,323,680 | - |
| 9. | Climate Change - German Dev't Bank (KfW) - (FLLoCA -CCRI Grant) | 390,000,000 | 16,968,438 |
| 10. | Climate Change - IDA World Bank (FLLoCA) | 11,000,000 | 11,000,000 |
| 11. | Urban Institutional Grant (UIG) | 35,000,000 | 32,309,300 |
| 12. | Migori Municipality URB Dvt Grant | 54,181,008 | - |
| 13. | Awendo Municipality URB Dvt Grant | 16,800,000 | - |
| 14. | Rongo Municipality URB Dvt Grant | 16,800,000 | - |
| 15. | Kehancha Municipality URB Dvt Grant | 16,800,000 | - |
| 16. | Grant from National Government - Industrial Park | 250,000,000 | 54,131,579 |
| 17. | Kenya Water and Sanitation (K-WASH) Program | 199,874,000 | - |
| 18. | National Agricultural Value Chain Development Project (NAVCDP) | 250,000,000 | 71,537,277 |
| 19. | Kenya Devolution Support Program II | 37,500,000 | - |
| 21. | Leasing of Medical Equipment | 124,723,404 | - |
| 22. | Fertilizer Subsidy | 144,621,807 | - |
| 23. | Allocation for Court fines | 974,165 | - |
| 24. | Allocation for Mineral Royalties | 3,125,408 | - |
| 25. | Basic Salary arrears for County Government Health Workers | 27,687,815 | - |
| 26. | Community Health Promoters (CHPs) Projects | 88,380,000 | - |
| 27. | MIGORI COUNTY CLIMATE CHANGE FUND FLOCCA Balances C/Fwd | 372,833,613 | 372,833,613 |
| 28. | MIGORI COUNTY HEALTH SPECIAL Balances C/Fwd | 915,068 | 915,068 |
| 29. | MIGORI COUNTY RMLF Balances C/Fwd | 681,918 | 681,918 |
| 30. | MIGORI COUNTY NARIGP OPERATIONS ACCOUNT Bal. C/Fwd | 4,261,826 | 4,261,826 |
| 31. | MIGORI COUNTY AGRICULTURE CHAIN Balances C/Fwd | 161,794,532 | 161,794,532 |
| 32. | MIGORI COUNTY INDUSTRIAL PARK Balances C/Fwd | 1,500,000 | 1,500,000 |
| Sub-total |  | 2,273,500,528 | 738,366,051 |

### 2.2.3 Own Source Revenue

During the reporting period, the County Government of Migori generated Kshs. 691,555,585.15 in Own Source Revenue (OSR) against a revised annual target of Kshs. 800,000,000. This translates to a performance rate of 86.4 percent. The OSR grew by Kshs. 178,989,275.15 (34.9 percent) compared to the previous year’s collection of Kshs. 512,566,310. The amount collected accounted for 6.6 percent of the total actual receipts (Kshs. 10,503,423,997) for the period.

This improved performance is attributed to enhanced digitization of revenue streams, especially in the administration of Single Business Permits and the Facility Improvement Fund (FIF).

Figure 4 below show the trend in OSR collection from FY 2017/18 to FY 2024/25 and the top-performing revenue streams for FY 2024/25. Respectively.

Figure 4: Own source Revenue collection trend from the FY 2017/18 to FY 2024/25

The top three performing revenue streams during the reporting period include Health/Hospital Facility Improvement Fund, Single Business Permits and Market Dues as shown in table 5 and figure 5 below. This is attributed to the increased automation and efficiency in the own source collection in the county.

Table 5: The top 5 performing revenue streams for the FY 2023/24

| OSR Revenue Stream | Amount (Kshs. Million) | % Contribution to Total OSR |
| --- | --- | --- |
| Health/Hospital Fees/FIF | 354.19 | 51.2% |
| Single Business Permits (SBP) | 74.54 | 10.8% |
| Market Dues | 31.43 | 4.5% |
| Billboards | 27.98 | 4.0% |
| Bus Park | 27.81 | 4.0% |
| Maize/Rice Cess | 27.53 | 4.0% |
| Distribution Permits | 22.75 | 3.3% |
| Sale of Assets | 19.15 | 2.8% |
| Other Sources | 106.19 | 15.4% |
| Total | 691.56 | 100.0% |

As illustrated in Figure 5 and Table 5, the leading source of Own Source Revenue (OSR) during FY 2024/25 was Hospital Fees under the Facility Improvement Fund (FIF), which generated Kshs. 354.19 million, accounting for 51 percent of total OSR receipts followed by revenue from Single Business Permits (SBP), which contributed 10 percent. The dominance of these streams underscores the critical role of health sector reimbursements and business licensing in the County’s local revenue mobilization efforts. Their performance reflects the impact of targeted automation, legislative reforms, and strengthened enforcement measures implemented during the reporting period.

Figure 5: Percentage performance for the top 5 performing revenue streams for the FY 2023/24

To further strengthen Own Source Revenue (OSR) performance, the County Government of Migori will prioritize the implementation of the Public Finance Management (County Revenue Administration) Act, in tandem with the newly enacted National Rating Act, 2024, which establishes a comprehensive legal framework for levying rates on land and buildings. In addition, the County will participate in the rollout of the National Treasury’s Revenue Forecasting Tool to improve the accuracy of revenue projections. Capacity building for revenue officers will also be undertaken to enhance governance, transparency, and operational efficiency in revenue administration.

## 2.3 Exchequer Releases and Returned Issue

During the period under review, total receipts to the county amounted to 10.503 billion comprising of exchequer releases of Kshs.9.81 billion (93.45%) and returned issue of Kshs.688.43 million (5.67%) respectively as shown in table 6 below.

Table 6: Exchequer release as a percentage of the total revenue received

| Category | REVENUE STREAM | AMOUNT RECEIVED KSHS. | AMOUNT RECEIVED AS A PERCENTAGE OF TOTAL REVENUE RECEIVED |
| --- | --- | --- | --- |
| Exchequer Releases | Equitable Share | 8,385,076,709.00 | 79.83% |
|  | Own Source Revenue | 691,555,585.15 | 6.58% |
|  | Other Receipts (donor funds, conditional grants etc.) | 738,366,050.90 | 7.03% |
|  | Subtotal-Exchequer | 9,814,998,345.05 | 93.45% |
| Returned Issue | Returned Issue | 688,425,652 | 6.55% |
| Total |  | 10,503,423,997.05 | 100.00% |

Exchequer Releases

During FY 2024/25, total exchequer issues from the County Revenue Fund (CRF) amounted to Kshs. 9.71 billion, comprising Kshs. 2.38 billion for development expenditure and Kshs. 7.33 billion for recurrent expenditure.

A breakdown of the exchequer releases is as follows:

- The County Executive received a total of Kshs. 8.70 billion, of which Kshs. 2.32 billion was allocated to development programmes and Kshs. 6.38 billion to recurrent programmes.

- The County Assembly received Kshs. 1.01 billion, with Kshs. 54.56 million directed towards development and Kshs. 950.82 million towards recurrent expenditure.

The composition of the exchequer issues indicates that 24.5% of the total funds were allocated to development programmes, while 75.5% supported recurrent operations. This is shown in table 7 below.

Table 7: Total Exchequer Issues in   FY 2024/25

| Exchequer Issues | Development (Kshs.) | Recurrent (Kshs.) | Total Exchequer Issues in FY 2024/25 (Kshs.) |
| --- | --- | --- | --- |
| County Executive | 2,321,274,792 | 6,379,336,644 | 8,700,611,436 |
| County Assembly | 54,563,768 | 950,815,575 | 1,005,379,343 |
| Total | 2,375,838,560 | 7,330,152,219 | 9,705,990,779 |
| % Exchequer issues | 24.5% | 75.5% | 100.0% |

## 2.4 Overall Expenditure Review

This section presents an overview of the County’s budget execution performance for the period under review, categorized by economic classification. The analysis highlights absorption rates as indicators of budget implementation efficiency across recurrent and development expenditures.

The approved budget for FY 2024/25 stood at Kshs. 12.15 billion, with Kshs. 7.68 billion allocated to recurrent expenditure and Kshs. 4.47 billion to development programmes. Actual expenditure amounted to Kshs. 10.12 billion, resulting in an overall absorption rate of 83 percent.

Development expenditure totaled Kshs. 2.79 billion, reflecting a 62 percent absorption rate against the approved allocation. The underperformance is primarily attributed to cash flow constraints, notably the non-disbursement of conditional grants and donor funds. Of the Kshs. 2.27 billion budgeted under this category, only Kshs. 738.37 million was received, representing a 32.5 percent realization rate. This shortfall significantly affected the implementation of development projects, underscoring the need for improved coordination with funding agencies and timely release of earmarked resources.

Table 8 below provides a summary of the expected and actual expenditure by classification.

Table 8: Summary of Budgeted Versus Actual Expenditure by Economic Classification for FY 2024/25

| Expenditure Classification | Budget (Kshs.) | Expenditure (Kshs) | Overall Absorption |
| --- | --- | --- | --- |
| Recurrent Expenditure | 7,680,595,273 | 7,329,816,757 | 95% |
| Development Expenditure | 4,466,410,306 | 2,790,612,450 | 62% |
| Total | 12,147,005,579 | 10,120,429,207 | 83% |

Figure 6 below gives an overview of the actual expenditure recurrent and development expenditure as released by the controller of budget during the period under review.

Figure 6: Comparison of recurrent versus development expenditure

2.4.1 Expenditure by economic classification.

Expenditure analysis by economic classification for FY 2024/25 reveals that the County Government incurred Kshs. 7.33 billion in recurrent spending against an approved allocation of Kshs. 7.68 billion, resulting in an absorption rate of 95 percent. Of this, Kshs. 3.74 billion was directed towards compensation to employees, achieving full absorption, while Kshs. 3.59 billion was utilized for operations and maintenance, reflecting a 91 percent absorption rate. Development expenditure amounted to Kshs. 2.79 billion against budgeted Kshs. 4.47 billion, translating to a 62 percent absorption rate. In total, the County spent Kshs. 10.12 billion out of the approved Kshs. 12.15 billion, representing an overall budget absorption of 83 percent as shown in Table 9 below.

Table 9: Expenditure analysis by economic classification

| Expenditure Classification | Budget (Kshs.) | Expenditure (Kshs.) | Overall Absorption |
| --- | --- | --- | --- |
| Total Recurrent Expenditure | 7,680,595,273 | 7,329,816,757 | 95% |
| Compensation to Employees | 3,733,634,096 | 3,743,112,919 | 100% |
| Operations and Maintenance | 3,946,961,177 | 3,586,703,838 | 91% |
| Development Expenditure | 4,466,410,306 | 2,790,612,450 | 62% |
| Total | 12,147,005,579 | 10,120,429,207 | 83% |

### 2.4.2 Analysis of Recurrent Expenditure

The total recurrent budget for the period under review was Kshs. 7.68 billion, against which actual expenditure was Kshs. 7.33 billion, resulting in an absorption rate of 95 percent. This indicates strong performance in meeting recurrent obligations, particularly in the areas of personnel emoluments and operational costs.

#### 2.4.2.1 Compensation of employees

During FY 2024/25, the County Government of Migori allocated Kshs. 3.73 billion for compensation to employees, with actual expenditure amounting to Kshs. 3.74 billion. This reflects full absorption of the allocated budget, with the slight variance attributed to the implementation of long-pending staff promotions during the reporting period. This performance affirms the County’s commitment to meeting payroll obligations and sustaining workforce stability, in line with the fiscal responsibility principles outlined in the Public Finance Management (PFM) Act, 2012. An analysis of personnel emoluments over the period FY 2017/18 to FY 2024/25, as illustrated in Figure 7 below, reveals a consistent upward trend, with expenditure rising from Kshs. 2.76 billion in FY 2017/18 to Kshs. 3.74 billion in FY 2024/25. This trajectory underscores the County’s prioritization of employee compensation as a key component of recurrent expenditure.

In line with Regulation 25(1)(c) of the PFM (County Governments) Regulations, 2015, the expenditure on employee compensation during the reporting period represented 35.6 percent of the actual revenue of Kshs. 10.50 billion representing a 4 percent increase compared to the Kshs. 3.60 billion reported in FY 2023/24. Of the total compensation, Kshs. 1.49 billion was attributed to personnel in the Health Sector, accounting for 40 percent of the overall wage bill.

Figure 7: Trend in Personnel Emoluments from FY 2017/18 to FY 2024/25

#### 2.4.2.2 Operations and Maintenance (Use of Goods and Services)

During FY 2024/25, the County Government allocated Kshs. 3.95 billion for Operations and Maintenance (O&M). Actual expenditure under this category amounted to Kshs. 3.59 billion, translating to an absorption rate of 91 percent. This performance reflects prudent utilization of resources towards the provision of essential services and operational support across departments. It also demonstrates effective budget execution and underscores the County’s commitment to sustaining service delivery through adequate funding of operational activities. Key expenditure items under O&M included specialized materials and supplies, office and general services, hospitality, training, and routine maintenance of assets.

#### 2.4.2.3 Facility Improvement Financing

During the FY 2024/25, the County Government of Migori recorded total collections amounting to Kshs. 354.19 million under the Facility Improvement Fund (FIF), representing 142 percent performance against the annual target of Kshs. 250 million. In line with the provisions of the Facility Improvement Financing Act, 2023, the collected revenue was retained and utilized at source to support health service delivery.

During the same period, total expenditure by health facilities under the FIF framework amounted to Kshs. 180.95 million, translating to an absorption rate of 72 percent against the approved budget of Kshs. 250 million. Table 11 below presents the expenditure performance by level of health facility.

Table 10: Migori County Health Facilities Expenditure Performance in FY 2024/25

| No. | Level of Health Facility | Number of Health Facilities | Approved Budget for the Facilities (Kshs.) | Actual Expenditure of the Facilities (Kshs.) | Absorption rate () |
| --- | --- | --- | --- | --- | --- |
| 1. | Level 5 Health Hospitals | 1 | - | 108,453,800 | - |
| 2. | Level 4 Health Hospitals | 15 | - | 70,883,346 | - |
| 3. | Level 2 & 3 Health Facilities | 138 | - | 1,611,474 | - |
|  | Total | 154 | 250,000,000 | 180,948,621 | 72 |

### 2.4.3 Development Expenditure Analysis.

During FY 2024/25, development expenditure amounted to Kshs. 2.79 billion against an approved development budget of Kshs. 4.47 billion, translating to an absorption rate of 62 percent. This expenditure represents 27.6 percent of the total actual expenditure and 47.35 percent of the total development budget. The suboptimal performance in development expenditure is largely attributed to cash flow constraints, particularly in the disbursement of conditional grants and donor-funded allocations. This underscores the need for enhanced coordination with funding agencies and timely release of earmarked resources to improve budget execution in future periods.

## 2.4.3.1 Departments Expenditure Overview

In FY 2024/2025, the total departmental expenditure amounted to Kshs. 10.12 billion against an approved budget of Kshs. 12.15 billion, translating to an overall absorption rate of 83.3 percent. Recurrent expenditure stood at Kshs. 7.33 billion compared to an allocation of Kshs. 7.68 billion, reflecting a utilization rate of 95.4 percent. Development expenditure amounted to Kshs. 2.79 billion against an allocation of Kshs. 4.47 billion, representing an absorption rate of 62.5 percent. Table 10 below presents a summary of the approved budget allocations, actual expenditures, and absorption rates across departments for both recurrent and development votes.

Table 11: Analysis of budget performance by department

| Department | Budget Allocation (Kshs. Millions) |  | Expenditure (Kshs. Millions) |  | Absorption rate (%) |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Rec | Dev | Rec | Dev | Rec | Dev |
| Agriculture, Livestock, Veterinary Services, Fisheries & Blue Economy | 237,954,615.00 | 720,729,020.00 | 227,784,261.68 | 264,914,501.40 | 95.7% | 36.8% |
| Trade, Tourism, Industry, Market & Cooperative Development | 150,892,995.00 | 362,948,374.00 | 134,728,374.45 | 243,570,088.00 | 89.3% | 67.1% |
| Health Medical Services | 1,836,306,496.00 | 307,378,792.00 | 1,791,204,795.15 | 124,128,353.00 | 97.5% | 40.4% |
| Education, Gender inclusivity, Social Services, Youth and Sports | 488,122,447.00 | 169,960,067.00 | 443,361,305.74 | 145,735,797.00 | 90.8% | 85.7% |
| Roads, Transport, Public Works & Infrastructural Development | 151,670,597.00 | 946,877,111.00 | 150,496,857.49 | 925,799,841.00 | 99.2% | 97.8% |
| Lands, Physical Planning, Housing & Urban Development | 113,718,312.00 | 99,790,941.00 | 113,621,718.78 | 51,136,042.45 | 99.9% | 51.2% |
| Rongo Municipality | 22,419,989.00 | 31,316,634.00 | 22,419,989.00 | 8,966,655.00 | 100.0% | 28.6% |
| Kehancha Municipality | 25,129,118.00 | 27,850,000.00 | 25,129,110.00 | 13,437,206.00 | 100.0% | 48.2% |
| Migori Municipality | 21,139,996.00 | 64,349,602.00 | 18,182,705.00 | 3,966,620.00 | 86.0% | 6.2% |
| Awendo Municipality | 20,849,999.00 | 37,234,595.00 | 20,550,000.00 | 24,102,186.00 | 98.6% | 64.7% |
| Environment, Natural Resources, Climate Change & Disaster Management | 297,768,894.00 | 785,932,986.00 | 285,460,470.85 | 376,143,130.00 | 95.9% | 47.9% |
| Finance and Economic Planning | 1,151,226,840.00 | 28,133,040.00 | 1,146,237,036.23 | 26,632,040.00 | 99.6% | 94.7% |
| Public Service Management, Monitoring & Evaluation & Performance Contracting | 920,934,150.00 | 10,854,920.00 | 839,087,051.01 | 10,854,920.40 | 91.1% | 100.0% |
| County Executive | 431,801,813.00 | 153,460,461.00 | 431,260,245.49 | 141,293,441.00 | 99.9% | 92.1% |
| County Assembly | 968,733,221.00 | 102,916,959.00 | 950,808,145.30 | 54,410,484.78 | 98.1% | 52.9% |
| Water and Energy | 203,218,433.00 | 483,640,991.00 | 190,992,063.07 | 274,574,631.00 | 94.0% | 56.8% |
| Public Health & Sanitation | 526,868,558.00 | 133,035,813.00 | 465,815,583.62 | 100,946,513.00 | 88.4% | 75.9% |
| Office of the County Attorney | 111,838,800.00 | - | 72,677,044.00 |  | 65.0% | 0.0% |
| Total | 7,680,595,273.00 | 4,466,410,306.00 | 7,329,816,756.86 | 2,790,612,450.03 | 95.4329254 | 62.5% |

During the period under review, notable performance in development budget absorption was recorded by the Departments of Roads, Transport, Public Works and Infrastructure (97.8%), Finance and Economic Planning (94.7%), County Executive (92.1%), and Education, Gender Inclusivity, Social Services, Youth and Sports (85.7%). This reflects effective execution of infrastructure projects, strong contract management, and efficient implementation of development initiatives, particularly in education infrastructure and youth empowerment programmes.

Conversely, several departments recorded low absorption rates in their development budgets during the FY 2024/25. These include the Departments of Agriculture, Livestock, Veterinary Services, Fisheries and Blue Economy (36.8%), Health (40.0%), Environment, Natural Resources, Climate Change and Disaster Management (47.0%), and Lands, Physical Planning, Housing and Urban Development (51.2%). Among the municipalities, Rongo Municipality recorded an absorption rate of 28.0%, while Migori Municipality registered a significantly low rate of 6.0%. The underperformance across these entities is largely attributed to non-receipt of conditional grants and donor funds, which constrained the implementation of planned development activities. This highlights the need for strengthened coordination with funding partners and timely disbursement of earmarked resources to enhance budget execution and service delivery in subsequent periods.

### 2.5 Implication of Fiscal Performance for the FY 2024/25 in relation to Financial Objectives

In accordance with fiscal framework and performance analysis contained in Migori County’s CFSP 2024 the County Government of Migori undertook a series of fiscal measures aimed at enhancing revenue mobilization, maintaining budgetary balance, and promoting efficient resource utilization. The CFSP 2024 emphasized five key financial objectives, namely:

i) Strengthening Own Source Revenue (OSR)
The County Government prioritized the automation of revenue streams and enforcement of revenue laws to seal leakages and improve collection efficiency. During FY 2024/25, OSR amounted to Kshs. 691.56 million against the target of Kshs. 800 million, representing an achievement rate of 86.4 percent. This performance reflects significant progress in revenue administration and aligns with the CFSP objective of enhancing OSR.

iii) Prioritizing High-Impact Programmes
Budget execution focused on programmes aligned with the County Integrated Development Plan (CIDP III) and the Fourth Medium Term Plan (MTP IV). Recurrent expenditure absorption stood at 95 percent, while development expenditure reached 62 percent. Despite the shortfall in development spending—attributed to delayed disbursement of conditional grants—the County Government ensured that available resources were directed towards priority interventions, demonstrating commitment to strategic programme implementation.

iv) Reducing Pending Bills and Managing Liabilities
As at 30th June 2024, the County Government of Migori reported outstanding pending bills amounting to Kshs. 1.94 billion. This comprised Kshs. 1.76 billion attributed to the County Executive and Kshs. 184.72 million from the County Assembly. Within the Executive’s total, Kshs. 875.34 million related to recurrent obligations, while Kshs. 881.38 million was linked to development expenditure. During the FY 2024/25, the County Executive settled pending bills totaling Kshs. 1.32 billion, with recurrent payments accounting for Kshs. 724.05 million (55 percent) and development-related payments amounting to Kshs. 592.82 million (45 percent). The County Assembly cleared Kshs. 81.91 million, comprising Kshs. 42.31 million (52 percent) for recurrent activities and Kshs. 39.60 million (48 percent) for development-related obligations.

In summary, the fiscal performance for FY 2024/25 was broadly aligned with the financial objectives set out in the CFSP 2024. The County Government demonstrated prudent financial management, sustained service delivery, and compliance with key fiscal principles. Going forward, enhanced coordination with development partners and continued improvement in revenue administration will be critical to achieving full compliance and maintaining fiscal sustainability.

### 2.6 Fiscal Responsibility Principles

In line with the Constitution, the Public Finance Management (PFM) Act, 2012, the PFM Regulations, and the principles of prudent and transparent management of public resources, the County Government largely adhered to the fiscal responsibility principles as outlined in the statute:

- Section 107(2)(b) of the Public Finance Management (PFM) Act, 2012 requires that at least 30 percent of the County Government’s budget be allocated to development programmes. In FY 2024/25, the allocation to development expenditure was Kshs. 4.47 billion, representing 36.8 percent of the total approved budget of Kshs. 12.15 billion—indicating compliance at the allocation level. However, actual development expenditure amounted to Kshs. 2.79 billion, translating to 27.6 percent of the total actual expenditure of Kshs. 10.12 billion. This shortfall in actual spending is majorly attributed to delayed disbursement of conditional grants and donor funds.

- Section 107(2)(c) of the Public Finance Management (PFM) Act, 2012 requires that a County Government’s recurrent expenditure shall not exceed its total revenue. In FY 2024/25, recurrent expenditure amounted to Kshs. 7.33 billion. This was within the total revenue envelope of Kshs. 12.15 billion confirming compliance with the fiscal responsibility threshold. The County Government ensured that recurrent obligations, including compensation to employees and operations and maintenance, were sustainably financed from available revenue. This reflects prudent fiscal management and adherence to the principles of responsible budgeting as outlined in the PFM Act.

- Pursuant to Section 107(2) of the PFM Act, 2012, Section 25(i)(b) of the Public Finance Management (County Governments) Regulations, 2015, requires that expenditure on wages and benefits for public officers shall not exceed thirty-five (35) percent of a County Government’s total revenue. In FY 2024/25, the County Government of Migori spent Kshs. 3.74 billion on compensation to employees, representing 35.6 percent of the actual total revenue of Kshs. 10,503,423,997. This reflects full absorption of the allocated budget and demonstrates the County’s commitment to meeting payroll obligations. Therefore, the wage bill remains within acceptable limits relative to total revenue.

- Section 25(i)() of the PFM Act, 2012 stipulates that borrowing shall be used only for financing development expenditure and not recurrent operations. During the FY 2024/25, the County Government did not undertake any borrowing to finance its budget, thereby remaining compliant with this fiscal responsibility principle.

### 2.8 Non-financial performance.

This section provides a summary of the key projects implemented by the County Government of Migori during FY 2024/25 across various sectors. The highlights presented herein are indicative of progress made in service delivery and infrastructure development. For a comprehensive account of all projects, including specific locations, and implementation status, refer to Annex 2 of this CBROP.

a) Agriculture, Livestock, Veterinary Services, Fisheries and Blue Economy

During the reporting period, the sector recorded notable achievements in seed distribution, surpassing targets for maize and bean seeds with 4,392 and 4,390 farmers reached respectively, against a target of 3,000. However, distribution of horticultural and rice seeds fell short, reaching only 1,200 and 300 farmers respectively. In livestock development, the distribution of galla goats was 80% complete, while infrastructure projects such as livestock loading ramps and inspection crushes were initiated and progressed to various stages of completion.

Veterinary services registered significant progress with the completion of Phase II of the diagnostic laboratory and renovation of the Nyasare slaughterhouse. In fisheries, 17 new fishponds were constructed and 30 existing ones renovated. Distribution of fish feeds and predator nets was successfully undertaken.

b) Education, Gender Inclusivity, Social Services, Youth and Sports

The sector achieved full implementation of targeted Early Childhood Development Education (ECDE) infrastructure projects. A total of 115 ECDE classrooms, 23 toilets, and 57 previously stalled ECDE projects were completed through community-driven initiatives. Sports infrastructure development was successfully executed, with playgrounds and stadiums completed in Got Kachola, Ntimaru East, Kachieng, and Wiga. Vocational Education and Training Centres (VETCs) in Tagare, Nyabasi East, and Central Sakwa reached Phase I completion, while procurement processes for Nyamador VETC were ongoing at the close of the financial year.

c) Environment, Natural Resources, Climate Change and Disaster Management

Despite ambitious targets, implementation in this sector was constrained by funding shortfalls, particularly due to non-disbursement of conditional grants and donor funds. The School Greening Programme achieved partial success, with 350,000 seedlings supplied against a target of 500,000. Most planned climate change and disaster management interventions were not implemented, underscoring the need for enhanced coordination with development partners and timely release of earmarked resources.

d) Health Services and Sanitation

The health sector recorded substantial progress in both medical services and public health infrastructure. Medical equipment was supplied to Migori County Referral Hospital (MCRH), Awendo, and Rongo Sub-County Hospitals. Key infrastructure projects—including maternity units, ablution blocks, fencing, and latrines—were completed across Nyatike, Suna West, Uriri, and other sub-counties. Public health interventions such as dispensary renovations, staff housing, and latrine construction were largely completed, with a few projects still ongoing. Notably, the refurbishment of the mental health clinic and installation of plumbing works at MCRH were finalized during the period.

e) Lands, Housing, Physical Planning and Urban Development

Progress was recorded in key planning initiatives, including the ongoing preparation of the Kehancha Municipality Land Use Development Plan and the valuation roll for Rongo Sub-County Urban Areas. Additionally, land acquisition for project implementation and land banking was achieved, with three parcels purchased.

f) Municipal Development (Rongo, Awendo, Kehancha and Migori)

Municipal development projects exhibited varied performance across the four municipalities. Rongo Municipality completed beautification works and road maintenance; Awendo Municipality finalized electrical installations and feasibility studies; Kehancha Municipality successfully completed road works and fenced a vehicle park; while Migori Municipality completed recreational park works, shoe shiner booths, and drainage maintenance.

g) Office of the Governor and ICT

The construction of the County Headquarters and GIS Laboratory progressed to 68% and 65% completion respectively. ICT initiatives were fully implemented and achieved 100% completion. These included internet subscriptions across county offices, recruitment of ICT officers, procurement of desktop computers, laptops, POS devices, and printers. System maintenance for Human Resource Management (HRM), electronic document management, and county websites was successfully undertaken.

h) Roads, Transport, Public Works and Infrastructure Development

Migori County made significant strides in infrastructure development, with over 60 road projects initiated across various wards and sub-counties. These projects aimed to enhance connectivity and accessibility, especially in rural and underserved areas reflecting the county’s commitment to improving transport networks. Other notable developments included township road upgrades in Isebania and the construction of footbridges such as the Acuth–Corona footbridge. These interventions are expected to boost trade, ease movement, and improve access to essential services.

- Trade, Tourism, Industry, Market and Cooperative Development

The county focused on supporting small-scale traders and enhancing market infrastructure. A major achievement was the construction of over 40 bodaboda sheds across various wards, providing shelter and organization for motorcycle operators. Numerous market shades and public toilets were also completed, including those at Kugitimo, Masangora, Mukuro, and Mapera markets. Additionally, the county successfully delivered essential supplies such as motorcycles, branded stationery, staff uniforms, mobile phones, and sanitation materials to support departmental operations.

j) Water and Energy

In the water sector, the county implemented a wide range of projects including borehole drilling, equipping, spring protection, and pipeline extensions. Successful projects such as the Nyabohanse, Kadika, Nyamaranya, and Dago boreholes, as well as the rehabilitation of Agongo Hill Spring, have significantly improved access to clean water.

On the energy front, the county installed solar streetlights and floodlights in over 20 wards, enhancing security and extending business hours in market centers. Repairs and maintenance of existing solar and grid-powered lighting systems were also completed. Notably, a transformer was installed at St. Kizito in Bukira Central to facilitate power distribution to 50 households. These energy interventions have contributed to improved public safety and economic activity in the targeted areas.

# SECTION THREE: RECENT ECONOMIC OUTLOOK

## 3.1 Macroeconomic and Financial Developments

Kenya’s economy remained resilient in 2024, growing by 5.2 percent, following a stronger growth of 5.6 percent in 2023 and 4.9 percent in 2022. This growth was supported by the diversified nature of the economy and proactive government interventions, despite challenges such as the withdrawal of the Finance Bill 2024, elevated fuel and food prices, and global disruptions stemming from the Russia-Ukraine conflict.

The Central Bank raised the policy rate by 375 basis points to 12.5 percent to anchor inflation expectations. The fiscal deficit narrowed from 7.0 percent of GDP in 2023 to 4.8 percent in 2024, attributed to improved revenue mobilization. Public debt declined from 70.8 percent of GDP in 2023 to 65.6 percent in 2024, largely due to currency appreciation. The current account deficit narrowed from 5.2 percent to 4.9 percent of GDP, driven by reduced trade deficits and increased secondary income inflows. Import cover declined from 4.3 months to 3.6 months, reflecting reserve drawdowns, while the Kenyan shilling depreciated by 24 percent year-on-year in 2023.

The banking sector remained stable, with capital adequacy at 18.6 percent, above the 14.5 percent prudential minimum, and a liquidity ratio of 49.7 percent, exceeding the 20 percent threshold. However, non-performing loans rose from 13.6 percent in 2022 to 14.5 percent in 2023, with high concentration in manufacturing, real estate, and household sectors.

Social indicators showed mixed performance. Poverty increased from 33.6 percent in 2019 to 36.1 percent in 2021, while unemployment rose slightly from 13.3 percent in 2021 to 13.9 percent in 2022. Income inequality also worsened, with the Gini coefficient increasing from 0.36 in 2020 to 0.39 in 2021.

## 3.2 Domestic Economic Growth Outlook

Kenya’s GDP is projected to grow by 6.0 percent in 2025 and 6.4 percent in 2026, driven by robust performance in the services sector and household consumption. Inflation is expected to decline to 5.5 percent in 2025 and 4.5 percent in 2026, supported by easing food and global price pressures. Monetary policy is anticipated to remain accommodative, underpinned by stable inflation and exchange rate expectations.

### 3.2.1 County Economic Outlook for FY 2025/2026

In line with the County Fiscal Strategy Paper (CFSP) 2025 and the Annual Development Plan (ADP) 2025/26, Migori County has prioritized completion of ongoing projects to ensure value for money and community benefit. The County will also expand infrastructure to enhance connectivity and service delivery, invest in food and nutrition security to improve livelihoods, and promote socio-economic transformation across sectors.

Building on this strategic direction, Migori County’s medium-term development agenda will be implemented through targeted sectoral priorities. These priorities aim to translate the county’s overarching goals into actionable programmes that enhance infrastructure, promote food security, and drive inclusive socio-economic transformation. The key focus areas are outlined below:

    - County Medium-Term Priorities

To operationalize the county’s strategic direction for FY 2025/26, the following medium-term priorities have been identified across key sectors:

- Infrastructure Development:

  - Upgrade access roads

  - Rehabilitate bridges and culverts

  - Maintain existing road networks to improve mobility and economic activity

- Food and Nutrition Security:

  - Promote agricultural mechanization

  - Provide certified inputs and encourage sustainable practices

  - Support value addition in agriculture, livestock, and fisheries

  - Improve food access through livelihood support and donor partnerships

  - Strengthen the food value chain and resilience to climate shocks

- Socio-Economic Transformation:

  - Strengthen healthcare systems

  - Expand water supply infrastructure

  - Promote renewable energy

  - Enhance ECDE and vocational training facilities

- Youth Empowerment:

  - Support sports, arts, and cultural development initiatives

- Good Governance:

  - Promote transparent and accountable public service delivery

  - Ensure prudent financial management

  - Strengthen partnerships for inclusive development

Details of the economic programmes and sub-programmes supporting these priorities are elaborated in Chapter Three of the ADP 2024/25 and 2025/26.

### 3.2.3 Capital Development Projects

A summary of key capital projects planned for implementation during the medium-term is provided in the ADP 2025/26 and 2026/27. These include infrastructure upgrades such as Awendo Modern Library and County Assembly Chambers, climate resilience projects including climate-smart roads and fire stations, water and food security initiatives like borehole drilling and irrigation kits, education and social services infrastructure such as ECDE classrooms and village offices, urban planning and green economy projects including land use plans and solar lighting, road development projects like upgrading C727 Junction–Chamgiwadu Road, and livestock market infrastructure such as inspection crushes. Each project includes details on cost, funding sources, implementation timelines, performance indicators, and alignment with cross-cutting issues such as climate change and disability inclusion.

The following table presents a selection of capital development projects planned for implementation, categorized by sector and aligned with the county’s strategic priorities.

| Subprogram | Project name and location | Description of activities | Estimated cost |  | Source of funds | Time frame (q1, q2, q3, q4) | Performance indicator | Target | Status (New/Ongoing) | Implementing agency |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sector: County Executive |  |  |  |  |  |  |  |  |  |  |  |
| Programme Name: E- learning |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure development | Upgrade of Awendo Modern Librar | Upgrade of Awendo Modern Library |  | 35M | MCG | 3yrs | No of student doing research | 1 | Ongoing | MCG |  |
| Sector: County Assembly |  |  |  |  |  |  |  |  |  |  |  |
| Programme Name: Infrastructure development |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Development | Construction of postmodern County Assembly Chambers | Requisition |  | 700M | County government |  | National Government | 1 | New | County Assembly/public works |  |
|  |  | Advertisement/publishing |  |  |  |  | County Government |  |  |  |  |
|  |  | Opening |  |  |  |  |  |  |  |  |  |
|  |  | Evaluation |  |  |  |  |  |  |  |  |  |
|  |  | Professional opinion |  |  |  |  |  |  |  |  |  |
|  |  | Award |  |  |  |  |  |  |  |  |  |
|  |  | Contract agreement |  |  |  |  |  |  |  |  |  |
|  |  | Project actualization |  |  |  |  |  |  |  |  |  |
|  |  | Inspection |  |  |  |  |  |  |  |  |  |
| Sector: Environment (under Flocca related activities) |  |  |  |  |  |  |  |  |  |  |  |
| Programme Name: Climate Change Adaptation and Mitigation |  |  |  |  |  |  |  |  |  |  |  |
| Climate change adaptation & Mitigation | Support alternativlihoods | Support grafted fruits, energy venture, tree nursery production |  | 65M | MCG | Q1-4 | No. of ventures supported | 4 | New | Env Dept. |  |
| Water security | Support water supply | Rehabilitate pans, dam, drill boreholes |  | 357M | MCG | Q1-4 | No. of Pans rehabilitated, boreholes drilled and springs protected | 40 | New | Envt Dept |  |
| Food security | Improve food production | Provide irrigation kits, install greenhouses, provide drought tolerant crops and breeds |  | 350M | MCG | Q1-4 | No. of irrigation kits, Greenhouse, drought tolerant seeds, breeds provided, | 40M | New | Envt Dept |  |
| Climate proofing infrastructure | Construct climate smart infrastructure | Construct climate-smart roads, bridges |  | 110M | MCG | Q1-4 | No. of climate smart bridges constructed, No. of KM of climate-smart roads constructed, | 6 | New | Department of Environment |  |
| Programme Name: Disaster Management and Fire Rescue Services |  |  |  |  |  |  |  |  |  |  |  |
| Fire rescue services | Construct ultra-modern fire station | Construction and equipping (Phase 1) |  |  |  | Q1-4 | Fire station constructed | 1 | New | Envt Dept |  |
|  |  |  |  | 137M | MCG |  |  |  |  |  |  |
| Sector: Finance and Economic Planning |  |  |  |  |  |  |  |  |  |  |  |
| Programme Name: General administration |  |  |  |  |  |  |  |  |  |  |  |
| General administration | Construction of Finance Complex | Construction of the building (5 floors) |  | 50,000,000 | County Government of Migori | q1, q2, q3, q4 | % completion of the County store | 100 | Ongoing | Finance and economic planning |  |
| Sector: Lands, Housing and Physical Planning |  |  |  |  |  |  |  |  |  |  |  |
| Programme Name: Physical and Land Use Planning services. |  |  |  |  |  |  |  |  |  |  |  |
| Planning of urban areas | Preparation of Local Physical and Land Use Development Plans for Muhuru and Kegonga Towns | Inception Report |  | 80,000,000 | County government | Q1, Q2, Q3, Q4 | No of Local Physical and Land Use Development Plans Prepared | 2 | New | Physical Planning and Urban Development department |  |
|  |  | Public Participation |  |  |  |  |  |  |  |  |  |
|  |  | Survey Report |  |  |  |  |  |  |  |  |  |
|  |  | Draft Plan |  |  |  |  |  |  |  |  |  |
|  |  | Approval |  |  |  |  |  |  |  |  |  |
| Sector: Public Service Management |  |  |  |  |  |  |  |  |  |  |  |
| Programme Name: Devolved Units Administration Services |  |  |  |  |  |  |  |  |  |  |  |
| Devolved Units Development Services | Construction of Sub-County/Ward Offices | Sub County ward offices construction / renovation |  | 470M | County government | Q3 | No of Sub-County/Ward offices Constructed | 4 | New | PSM&D Department |  |
|  | Construction of 20 Village offices | Site clearing, office block, electrical works, 4 door pit latrine, two 10000 litres water tanks, fencing and gate |  | 100M | County government | Q3 | No of Village offices Constructed | 20 | New | PSM&D Department |  |
| Sector: Roads, Transport and Public Works |  |  |  |  |  |  |  |  |  |  |  |
| Programme Name: Road Development, Maintenance and Management |  |  |  |  |  |  |  |  |  |  |  |
| Road network improvement | UPGRADING TO BITUMEN STANDARD OF C727 JUCTION-KANYIMACH JUNCTION-CHAMGIWADU ROAD | Bituminous works |  | 450m | County government | Q1 , Q2, | Kms of the road to be upgraded | 13kms | ongoing | Roads department |  |
|  |  |  |  |  |  | Q3, |  |  |  |  |  |
|  |  |  |  |  |  | Q4 |  |  |  |  |  |
| Sector: Water and Energy |  |  |  |  |  |  |  |  |  |  |  |
| Programme Name: Water Supply and Management Services |  |  |  |  |  |  |  |  |  |  |  |
| Rural Water Services | Drilling of Boreholes (Countywide) | Drilling of borehole |  | 75m | CGM/National Government/Partners | Q2, Q3 | No. of boreholes drilled | 30 | New | Department of water/National Govt/Partners |  |
|  | Equipping of boreholes (Countywide) | Equipping of boreholes |  | 200m | CGM/National Government/Partners | Q2, Q3 | No. of boreholes equipped | 40 | New/Ongoing | Department of Water and Energy/National Govt/Partners |  |
| Sector; EDUCATION, GENDER INCLUSIVITY, SOCIAL SERVICES, YOUTH AND SPORTS |  |  |  |  |  |  |  |  |  |  |  |
| Programme Name: Early childhood development education services |  |  |  |  |  |  |  |  |  |  |  |
|  | Construction of ECDE classrooms and Toilets countywide | Construction of classrooms and toilets |  | 74m | CGM |  | No of ECDE classrooms and toilets Constructed | 120 | New | Department of education |  |
| Sector; Livestock Production |  |  |  |  |  |  |  |  |  |  |  |
| Programme Name: Livestock market development |  |  |  |  |  |  |  |  |  |  |  |
|  | Construction of Livestock Inspection crushes |  |  | 36 | CGM |  | Number of inspection crushes constructed | 120 | New |  |  |

## 3.3 Risks to the Economic Outlook

Key downside risks to the economic outlook include the following:

- adverse weather conditions due to climate change, rising recurrent expenditure pressures especially wage-related costs,

- revenue shortfalls and delayed exchequer releases leading to liquidity constraints,

- technological failures in systems such as IFMIS causing transaction delays, and

- external risks from geopolitical tensions and global financial tightening which may disrupt supply chains and commodity prices.

## 3.4 Mitigation Measures

To address the identified risks to the economic outlook, Migori County will continue to implement the following mitigation strategies:

  - Advocate for timely disbursement of funds: Align fund releases with procurement cycles through legislative frameworks to avoid implementation delays.

  - Enforce strict staffing policies: Hire only on a need basis and replace staff through natural attrition to manage wage-related expenditure pressures.

  - Automate remaining revenue streams: Enhance own-source revenue collection by digitizing all revenue channels and improving enforcement mechanisms.

  - Prioritize settlement of pending bills: Ensure financial discipline by clearing outstanding obligations before initiating new projects.

  - Strengthen climate resilience planning: Integrate climate-smart infrastructure across sectors and establish early warning systems and community-based disaster preparedness programs.

  - Improve public financial management systems: Enhance capacity in IFMIS usage and ensure backup protocols to reduce transaction delays and conduct regular financial audits and performance reviews.

  - Diversify revenue sources: Explore new local revenue streams such as tourism levies, land rates, and service fees and strengthen partnerships with development agencies and private sector investors.

  - Enhance monitoring and evaluation (M&E): fully operationalize the County Performance Management Framework and link M&E outcomes to budget allocation and project prioritization.

  - Promote inclusive governance and citizen engagement: Institutionalize public participation in planning and budgeting processes and use digital platforms for feedback, transparency, and accountability.

  - Strengthen procurement and contract management: Align procurement timelines with fund disbursement schedules and enforce accountability in contract execution and project delivery.

# SECTION FOUR: RESOURCE ALLOCATION FRAMEWORK

This section outlines the strategic framework guiding resource allocation for the 2026/27 financial year and the medium term. It provides an overview of the ongoing budget implementation, fiscal policy direction, revenue and expenditure projections, and the criteria used to prioritize funding across sectors. The framework is anchored on the principles of fiscal responsibility, equity, and alignment with county, national, and global development goals, ensuring that resources are allocated efficiently to maximize impact and value for money.

Implementation of the 2025/26 Budget

The implementation of the 2025/26 budget is still ongoing and continues to be guided by the 2025 County Fiscal Strategy Paper (CFSP), the  FY 2025/2026Annual Development Plan (ADP), and the County Integrated Development Plan (CIDP) 2023-2028. The county government remains committed to delivering services, sustaining development programs, and ensuring prudent use of public resources during the remaining part of the financial year.

Efforts are underway to strengthen own-source revenue collection through automation, enforcement of revenue laws, and expansion of the revenue base. Equitable share disbursements from the National Treasury and conditional grants are also being received progressively, supporting county operations and service delivery.

Recurrent expenditure, particularly on personnel, operations, and maintenance, continues to be implemented as planned. Development expenditure is ongoing, with several flagship projects currently under execution. The county has prioritized timely procurement processes and close monitoring of projects to enhance budget absorption and reduce delays.

As implementation progresses, the county is focusing on accelerating completion of ongoing projects, addressing revenue gaps, and enhancing efficiency in service delivery. The lessons being drawn from the current budget execution are informing the preparation of the medium-term framework and future resource allocation decisions.

Fiscal Policy for FY 2026/27 Budget and the Medium Term

The county’s fiscal policy for the 2026/27 financial year and the medium-term period will continue to focus on ensuring prudent management of public resources while supporting inclusive economic growth and improved service delivery. The fiscal stance is designed to balance between revenue mobilization, expenditure efficiency, and fiscal sustainability.

Revenue Policy The county will enhance its revenue performance by broadening the revenue base, sealing leakages, strengthening enforcement, and expanding automation of revenue collection systems. Emphasis will be placed on compliance, equity in taxation, and fair application of user charges and fees to minimize resistance while improving yield. The county also expects to continue receiving equitable share allocations and conditional grants from the national government, which will complement own-source revenue.

Expenditure Policy Expenditure priorities will be aligned with the County Integrated Development Plan (CIDP), the Annual Development Plan (ADP), and the County Fiscal Strategy Paper (CFSP). Priority will be given to:

- Strengthening social sectors such as health and education to improve human capital development.

- Expanding infrastructure, water supply, and agricultural productivity to stimulate economic growth.

- Supporting youth, women, and vulnerable groups through empowerment programs.

- Rationalizing recurrent expenditure, particularly personnel costs, to ensure resources are directed towards development programs.

Fiscal Responsibility In line with the Public Finance Management (PFM) Act, the county will maintain fiscal responsibility by:

- Ensuring development expenditure remains at least 30% of total expenditure.

- Maintaining the wage bill at sustainable levels.

- Managing pending bills and avoiding accumulation of arrears.

- Ensuring borrowing, where necessary, is sustainable and used strictly for development purposes.

Medium-Term Outlook Over the medium term, fiscal policy will remain focused on creating fiscal space for development while maintaining macroeconomic stability. The county Government will continue to improve budget credibility, enhance predictability in resource flows, and strengthen linkages between planning and budgeting. This will ensure the county government remains on track towards achieving its CIDP priorities, aligning with the National Government’s Medium-Term Plan and Vision 2030.

Fiscal projections

In FY 2026/27, total revenue is projected at Kshs. 11,364,674,007, comprising Kshs. 8,883,939,719 from the Equitable Share of revenue raised nationally, Kshs. 1,680,734,288 from Conditional Grants and donor funds, and Kshs. 800,000,000 from Own Source Revenue. This reflects a modest increase from the FY 2025/26 allocation of Kshs. 10,825,813,687. The County Government shall maintain a balanced budget, with no fiscal deficit anticipated, and therefore no external financing will be required. Recurrent and development expenditures will be fully financed within the projected revenue envelope.

Table 12: Fiscal Projections

| Revenue Category | Annual budget allocation FY2025/26 | Annual Projected Amount FY2026/27 |
| --- | --- | --- |
| Equitable Share of Revenue Raised Nationally | 8,385,079,399 | 8,883,939,719 |
| Conditional Grants/donor funds | 1,680,734,288 | 1,680,734,288 |
| Own Source Revenue | 760,000,000 | 800,000,000 |
| TOTAL | 10,825,813,687 | 11,364,674,007 |

FY 2026/27 and Medium-Term Budget Framework

The County Budget Review and Outlook Paper (CBROP) provide the basis for updating the Medium-Term Budget Framework. The framework guides resource allocation and fiscal discipline for the next three financial years in line with the county’s development agenda.

The framework links the county’s revenue projections, expenditure ceilings, and development priorities to the broader goals outlined in the County Integrated Development Plan (CIDP), the Annual Development Plan (ADP), and the Fiscal Strategy Paper (CFSP). It ensures consistency, predictability, and sustainability in the budget-making process.

Under the framework, sector ceilings are reviewed and adjusted to reflect revenue performance, emerging expenditure pressures, and public priorities identified during consultations. This allows the county government to balance recurrent needs, such as salaries and operations, and development spending on infrastructure and service delivery.

The framework also integrates fiscal responsibility principles, including adherence to the set ceilings on wage bills, debt levels, and development expenditure thresholds as provided by the Public Finance Management (PFM) Act. This promotes prudent management of resources while safeguarding fiscal sustainability.

The framework further aligns county priorities with the National Government’s Medium-Term Plan and Vision 2030 to ensure coherence in development goals. Through this approach, the county government can focus on inclusive growth, equity in resource distribution, and improved service delivery in key sectors such as health, education, agriculture, water, and infrastructure.

The Medium-Term Budget Framework serves as the financial anchor of the CBROP, providing a structured approach to planning, resource allocation, and implementation of county programs over the medium term. The resources shall be shared among the implementing departments as shown in the table below.

Table 13: Fiscal Projections for FY 2026/27 by Sector

| Sector | 2024/25 Approved Budget | 2025/26 Approved Budget | 2026/27 Projections |
| --- | --- | --- | --- |
| Agriculture, Livestock, Veterinary Services, Fisheries and Blue Economy | 777,004,117 | 630,997,873 | 662,406,109 |
| County Assembly | 1,037,472,209 | 957,920,178 | 1,005,601,137 |
| Office of the County Attorney | 128,000,000 | 92,780,857 | 97,399,071 |
| County Executive | 691,620,000 | 539,226,422 | 566,066,688 |
| Education, Gender inclusivity, Social services, Youth and Sports | 618,838,410 | 638,620,788 | 670,408,459 |
| Finance and Economic Planning | 985,006,053 | 656,443,483 | 689,118,287 |
| Lands, Physical Planning, Housing and Urban Development | 203,926,592 | 177,792,714 | 186,642,436 |
| Rongo Municipality | 46,800,000 | 40,922,009 | 42,958,923 |
| Awendo Municipality | 46,800,000 | 40,922,009 | 42,958,923 |
| Migori Municipality | 84,181,008 | 78,303,017 | 82,200,589 |
| Kehancha Municipality | 47,800,000 | 41,678,110 | 43,752,659 |
| Environment, Natural Resources, Climate Change and Disaster Management | 468,619,589 | 499,203,004 | 524,051,085 |
| Medical Services | 1,947,298,349 | 2,330,442,772 | 2,446,441,733 |
| Public Health & Sanitation | 568,834,045 | 392,354,028 | 411,883,647 |
| Public Service Management, Monitoring and Evaluation and Performance Contracting | 778,782,856 | 1,232,864,429 | 1,294,230,875 |
| Roads, Transport, Public Works and Infrastructural Development | 920,379,734 | 1,225,673,892 | 1,286,682,426 |
| Trade, Tourism, Industry, Market and Cooperative Development | 486,106,968 | 575,370,977 | 604,010,357 |
| Water and Energy | 549,421,934 | 674,297,125 | 707,860,603 |
| Total | 10,386,891,864 | 10,825,813,687 | 11,364,674,007 |

Criteria for Resource Allocation for FY 2026/27

The resource allocation framework for FY 2026/27 will be guided by the county’s strategic priorities as outlined in the County Integrated Development Plan (CIDP 2023–2027), the Annual Development Plan (ADP 2026/27), the County Fiscal Strategy Paper (CFSP), and sectoral plans. It will also be anchored on the principles of the Public Finance Management (PFM) Act, 2012, the Medium-Term Expenditure Framework (MTEF), the Kenya Vision 2030, and the Sustainable Development Goals (SDGs). The goal is to ensure that scarce resources are allocated efficiently, equitably, and in a manner that delivers maximum value to county residents while promoting fiscal discipline and sustainability.

Key Criteria for Resource Allocation

- Alignment with County Development Priorities: Resources will be directed to programmes and projects consistent with the CIDP, ADP, and sectoral strategies. Priority will be given to flagship programmes and interventions that contribute to county, national, and global development goals.

- Fiscal Responsibility and Sustainability: Allocations will comply with fiscal responsibility principles under the PFM Act, 2012. At least 30% of the budget will go to development expenditure, with recurrent costs kept at sustainable levels. Debt management and prudent spending will be key.

- Revenue Performance and Resource Envelope: Resource allocation will be guided by projected revenues from the equitable share, own-source revenue, grants, and donor support. Sectors with strong potential to enhance revenue generation will be supported to strengthen capacity.

- Equity and Inclusivity: Allocations will promote equitable development across wards and sub-counties. Marginalized areas and vulnerable groups—including youth, women, PWDs, and the elderly—will receive special consideration.

- Ongoing and Stalled Projects: Completion of ongoing and stalled projects will be prioritized over starting new ones to ensure value for money and reduce resource wastage.

- Impact and Value for Money: Projects will be evaluated based on expected socio-economic impact, cost-effectiveness, and contribution to job creation and poverty reduction. Initiatives with cross-sectoral benefits and high multiplier effects will receive preference.

- Sectoral and Spatial Balance: Allocations will reflect county priorities across sectors. Investments will also be guided by spatial planning principles to promote balanced growth in both rural and urban areas.

- Public Participation and Stakeholder Priorities: Resource allocation will incorporate outcomes from public participation and stakeholder consultations to ensure responsiveness to community needs.

- Climate Change, Disaster Preparedness, and Sustainability: Allocations will integrate climate change adaptation, environmental sustainability, and disaster risk reduction measures. Focus will be placed on resilience in agriculture, water, health, and infrastructure.

- Performance and Accountability: Funding will be tied to measurable outputs and adherence to monitoring and evaluation frameworks. Departments demonstrating efficient use of resources and achievement of set targets will receive priority.

The application of these criteria will ensure that FY 2026/27 resources are allocated fairly, efficiently, and in line with the county’s development agenda. By aligning allocations with the CIDP, ADP, and MTEF framework, the County Government will enhance service delivery, promote inclusive growth, strengthen fiscal discipline, and deliver tangible development outcomes to its citizens.

Public Participation and Stakeholder Involvement

In line with the constitutional requirements and the Public Finance Management Act, public participation and stakeholder engagement were undertaken in the preparation of this County Budget Review and Outlook Paper (CBROP). The process ensured that the views of citizens, community groups, civil society organizations, professional bodies, the private sector, and other stakeholders were incorporated in shaping the fiscal outlook and priority areas for resource allocation.

The county Government conducted consultative forums across all sub-counties where residents provided inputs on service delivery, expenditure priorities, revenue performance, and emerging development needs. Submissions were also received through written memoranda and sector working group meetings, enabling a broad spectrum of stakeholders to share their perspectives.

These engagements provided valuable insights on key development priorities. The county government also received feedback on fiscal discipline, the need for equitable resource distribution, and calls for efficiency in project implementation.

The inputs from these consultations have been considered and integrated into this CBROP to enhance transparency, accountability, and inclusivity in county planning and budgeting. This approach reaffirms the county’s commitment to participatory governance and strengthens the alignment between community needs, county plans, and resource allocation decisions.

# SECTION FIVE: CONCLUSION

The County Budget Review and Outlook Paper (CBROP) for FY 2024/25 has provided a comprehensive analysis of the fiscal performance for the period under review, highlighting key achievements, challenges, and strategic priorities for the medium term. The County Government of Migori demonstrated commendable adherence to fiscal responsibility principles as outlined in the Public Finance Management (PFM) Act, 2012, including maintaining recurrent expenditure within total revenue, allocating over 30 percent of the budget to development programmes, and keeping the wage bill within the prescribed threshold.

Despite notable progress in revenue mobilization, particularly in Own Source Revenue (OSR) and equitable share receipts—the underperformance in conditional grants and donor funding constrained development expenditure and affected the implementation of key projects. The County Government responded by undertaking expenditure rationalization and prioritizing high-impact programmes aligned with the CIDP III and MTP IV.

Consequently, the fiscal projections for FY 2026/27 indicate a stable revenue outlook of Kshs. 10.85 billion, with no anticipated fiscal deficit. The County Treasury will continue to strengthen revenue administration, enhance budget absorption, and promote prudent financial management. Sector Working Groups (SWGs) are urged to align their budget proposals with the priorities outlined in this CBROP and ensure efficient resource allocation during the preparation of the County Fiscal Strategy Paper (CFSP) 2026.

To sustain service delivery and accelerate socio-economic transformation, the County Government will deepen stakeholder engagement, pursue strategic partnerships, and leverage technology to improve governance and transparency. All departments and entities must remain committed to completing ongoing projects, resolving pending bills, and implementing mitigation measures against identified fiscal and operational risks.

## ANNEX 1: SCHEDULE FOR PUBLIC PARTICIPATION

### ANNEX 2: KEY ACHIEVEMENTS

#### 2.3.2.1 Agriculture, Livestock, veterinary services, fisheries and blue economy

Agriculture

| Project name and Location (Ward/Sub- county/ Countywide} | Description of activities | Target | Achievement | Status |
| --- | --- | --- | --- | --- |
| Crop development purchase of Maize Seed whole county | Recruitment of beneficiaries and distribution | 3,000 farmers | 4,392 farmers | Procured and distributed |
| Crop development Beans Subsidy whole county | Recruitment of beneficiaries and distribution | 3,000 farmers | 4,390 farmers | Seeds distributed to farmers |
| Assorted Horticultural seeds for demonstration whole county | Recruitment of beneficiaries and distribution | 1,800 farmers | 1,200 farmers | Seeds distributed to farmers |
| Purchase of rice seeds | Recruitment of beneficiaries and distribution | 500 farmers | 300 farmers | Seeds distributed to farmers |

#### Livestock production

| Project name and Location (Ward/Sub- county/ Countywide} | Description of activities | Target | Achievement | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| Livestock Breeds improvement | Beneficiary identification Procurement and distribution of in calf dairy heifers | 150 | 63 |  |  |
|  | Beneficiary identification Procurement and distribution Sahiwal breeding bulls | 240 | 21 |  |  |
|  | Beneficiary identification Procurement and distribution of galla goats | 60 | 20 | 80% completed |  |
| Livestock Enterprise development and value addition | Establishment of livestock feed formulation centers Beneficiary identification Procurement and distribution of feed formulation ingredients | 6 |  | Not done |  |
| Livestock market development | Site selection Construction of livestock loading ramps Tendering of construction services | 3 | 1 | 80% Completed |  |
|  | Site identification Tendering of construction services Construction of livestock Inspection crushes | 120 | 1 | 80% Completed |  |
| Livestock climate Change Adaptation and Mitiga tion | Beneficiary identification Procurement and distribution of Drought tolerant fodder planting materials/seeds | 10acres | 3 acres |  | Not completed |
|  | Beneficiary identification Procurement and distribution of livestock feeds | 1000 |  |  | Not completed |

#### Veterinary services

| Project name and Location (Ward/Sub- county/ Countywide} | Description of activities | Target | Achievement | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| Construction of veterinary diagnostic laboratory | Tendering Bill of quantities | Completion of phase 2 | Completed | Phase 2 done | To be completed in subsequent years |
| Renovation of Nyasare slaughterhouse | Tendering Bill of quantities supervision | 1 | Completed | Complete |  |
| Renovation of Nyasare slaughterhouse | Tendering Bill of quantities supervision | 1 | Completed | Complete |  |
| Procurement of vaccines and sera | Tendering | 100,000 | Partially done | complete |  |

#### Fisheries and Blue Economy

| Project name and location | Description of activities | Target | Achievements | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| Pond construction | Construction of new fishponds | 20 | 17 | Work in progress |  |
| Pond renovation | Renovation of existing fishponds | 40 | 30 | Not completed |  |
| Renovation of Nyangwina Fish Auction Centre | Renovation works | 1 | 50% | Renovation works yet to start | contractor on site |
| Supply and delivery of predator nets | Supply and distribution of predator nets to farmers | 20 | 20 | Delivered |  |
| Supply and delivery of pond liners | Supply and distribution of predator nets | 4 | 4 | delivered |  |
| Supply and delivery of patrol engine speed boat in Nyatike | Supply and delivery of boat engine | 1 | 0 | Not delivered | to be delivered in September |
| Supply and delivery of fish feeds | Supply and distribution of fish feeds | 7250 kgs | 7250 kgs | delivered |  |
| supply and delivery of life saving jackets | supply and delivery of life saving jackets | 400 | 0 | Not delivered |  |
| Construction of raised fishponds | construction of new fishponds | 4 | 4 |  |  |
| Supply and delivery of monosex Nile tilapia fingerlings | supply and delivery of monosex tilapia fingerlings | 100,000 | 0 | Not delivered | awaiting completion of constructed/ renovated fishponds |
| Completion of Phase II office block | Renovation works | 1 | 100% | Completed |  |

#### 2.3.2.3 Education, gender Inclusivity, Social services, Youth and Sports.

| Project name and Location (Ward/Sub- county/ Countywide} | Description of activities | Target | Achievement | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| Aeko playground (Got Kachola Ward) | Leveling of playground and construction of lavatory | 1 | 1 | Complete | Done |
| Ntimaru Stadium ( Ntimaru East Ward) | Levelling and grassing | 1 | 1 | Complete | Done |
| Sori playground (Kachieng) | Fencing | 1 | 1 | Complete | Done |
| Masara Primary playground (Wiga Ward) | Levelling and murraming | 1 | 1 | Complete | Done |
| Ngisiru VETC Tagare Ward) | Phase I construction of model VETC | 1 | 1 | Complete | Phase 1 completed |
| Kegonga VETC (Nyabasi East) | Phase I construction of model VETC | 1 | 1 | Complete | Phase 1 completed |
| Awendo Marindi VETC ( Central Sakwa) | Phase I construction of model VETC | 1 | 1 | Complete | Phase 1 completed |
| Nyamador VETC ) E/ Kamagambo |  | 1 | 1 | ongoing | Procurement ongoing |
| Construction of ECDE classrooms |  | 115 | 115 | Complete | Community projects |
| Construction of ECDE toilets |  | 23 | 23 | Complete | Community projects |
| Completion of previously stalled ECDEs |  | 57 | 57 | Complete | Community projects |

#### 2.3.2.4 Environment, Natural resources, climate change and disaster management

| Project name and Location (Ward/Subcounty/ Countywide) | Description of activities | Target | Achievement | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| School Greening programme | Supply tree seedlings to schools | 500,000 | 350,000 | Completed | NRM & Forestry Dev. Programme |
| Support alternative sources of livelihoods (Countywide) | Support fruit tree production | 20,000 | Not achieved | Not implemented |  |
|  | Establish juice processing plant | 1 | Not achieved | Not implemented |  |
|  | Support farmers to undertake bamboo production | 5,000 | Not achieved | Not implemented |  |
|  | Support the production of briquettes through youth, groups and women's groups for | 20 | Not achieved | Not implemented |  |
|  | Promote improved cook stoves | 20 | Not achieved | Not implemented |  |
|  | Support the community tree nursery to produce grafted fruit trees and other indigenous trees | 40 | Not achieved | Not implemented |  |
|  | Support nature-based enterprises (apiculture, hay production, aquaculture) | 8 | Not achieved | Not implemented |  |
| Water security | Rehabilitate water pans | 8 | Not achieved | Not implemented |  |
|  | Acquire, distribute & install 10,000L water tanks | 100 | Not achieved | Not implemented |  |
|  | Drilling and equipping of solar-powered boreholes | 10 | Not achieved | Not implemented |  |
|  | Undertake spring conservation | 40 | Not achieved | Not implemented |  |
| Food security | Acquire and distribute irrigation kits | 10 | Not achieved | Not implemented |  |
|  | Install greenhouses | 8 | Not achieved | Not implemented |  |
|  | Support farmers with drought-tolerant crops | 1000 | Not achieved | Not implemented |  |
|  | Support farmers with early-maturing crops | 1,000 | Not achieved | Not implemented |  |
|  | Acquire and distribute improved animal breeds | 8 | Not achieved | Not implemented |  |
| Climate-proofing infrastructure | Construct climate-smart bridges | 2 | Not achieved | Not implemented |  |
|  | Construct climate-smart roads |  | Not achieved | Not implemented |  |

#### 2.3.2.6 Health services and Sanitation

Medical services

| No | Tender Description | LPO Amount | Location | Status |
| --- | --- | --- | --- | --- |
| 1 | Supply And Delivery Of Medical Equipment For Mcrh | 2,999,600.00 | MCRH Hq | Completed |
| 2 | Supply, Delivery And Installation Of Equipment At Mcrh Mortuary | 3,950,800.00 | MCRH Hq | Ongoing |
| 3 | Completion Of Maternity At Macalder Sub County Hospital | 1,997,444.60 | Nyatike SC | 90% |
| 4 | Completion Of Ablution Block At Karungu Sub County Hospital | 1,999.917.80 | Nyatike SC | Completed |
| 5 | Construction Of Latrine At Godkwer And Nyamaraga Sub County Hospitals | 1,994,620.00 | Suna West SC | Completed |
| 6 | Completion Of Ablution Block At Macalder Sub County Hospital | 1,999,198.40 | Nyatike SC | Completed |
| 7 | Construction Of Modern Maternity Unit At Muhuru Sub County Hospital | 7,998,538.00 | Nyatike SC | Completed |
| 8 | Renovation Of Staff House At Muhuru Sub County Hospital | 1,989,585.60 | Nyatike SC | Completed |
| 9 | Relocation Of Pathway And Repair Of Main Gate At Mcrh | 1,999,840.00 | MCRH Hq | Completed |
| 10 | Refurbishment Of Mental Health Clinic | 3,999,338.00 | MCRH Hq | Completed |
| 11 | Installation Of Canopy ,Plumbing Works And Slab Repairs | 1,999,956.00 | MCRH Hq | Completed |
| 12 | Fencing Oyani Sub County Hospital | 1,999,956.00 | Uriri SC | Completed |
| 13 | Renovation Of Opd And Maternity Unit At Karungu Sub County Hospital | 1,997,299.00 | Nyatike SC | Completed |
| 14 | Supply, Delivery And Installation Of Medical Equipment For Awendo Sub County Hospital | 8,734,000.00 | Awendo SC | Delivered |
| 15 | Supply And Delivery Of Newborn Unit Commodities | 2,481,298.00 | Awendo SC | Delivered |
| 16 | Supply And Delivery Of Newborn Unit Equipment | 2,499,200.00 | Rongo SC | Delivered |
| 17 | Fencing Of Awendo Sub County Hospital | 4,994,496.00 | Awendo SC | Ongoing |
| 18 | Civil Works At MCRH Mortuary | 1,499,800.00 | MCRH Hq | Ongoing |

Public health

| S/No | Project description | Location | Estimate Amount | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
|  | Building of EPI store and SCHMT Block at Suna East | Suna Centrral | 9,961,882.80 | Complete |  |
|  | Renovation of Nyamekongoroto Dispensary | Masaba ward | 1,499,068.00 | Complete |  |
|  | Proposed renovation of Taragwiti Dispensary | Makerero ward | 1,707,172 | Complete |  |
|  | Proposed renovation of Alara Nyambija Dispensary | North Sakwa | 3,299,427.44 | 90% |  |
|  | Proposed renovation of Koduogo Dispensary | West Sakwa | 2,199,116.540 | Complete |  |
|  | Proposed Fencing and gate at Kitere Health centre | South Kamagambo | 1,647,200.00 | Complete |  |
|  | Proposed renovation of Koyar Dispensary | South Kamagambo | 391,500.00 | Complete |  |
|  | Proposed renovation of Ranjira Dispensary | Central Sakwa | 2,199,406.40 | Complete |  |
|  | Proposed Renovation of twin staff house at Kuja Nyokal Dispenasary | North Sakwa | 3,398,823.20 | Complete |  |
|  | Proposed renovation of Mariba Dispensary | Got Kachola | 569,560.00 | 70% |  |
|  | Proposed renovation of Tulu Dispensary | Got Kachola | 968,790.38 | Complete |  |
|  | Proposed Completion of Kotedo Dispensary | South Kanyamkago | 1,599,721,00 | Complete |  |
| AC 02 | Community Projects |  |  |  |  |
|  | Renovation of Mainangiti dispensary | Bukira Central | 699,654.00 | Work in progress |  |
|  | Construction of Toilet at Bondo Otuchi | Central Kamagambo | 499,495.00 | Complete |  |
|  | Completion of Kudho dispensary | East Kamagambo | 1,300,000.00 | Work in progress |  |
|  | Construction of 2 Door VIP Latrine at Ayego dispensary | God Jope | 400,000.00 | Work in progress |  |
|  | Construction of Gosebe Maternity ward | Gokeharaka/Getambwega | 2,499,602.80 | Completed |  |
|  | Construction of Maternity ward at Yago dispensary | Got Kachola | 1,399,424.00 | Work in progress |  |
|  | Construction of Kongabi dispensary at Bukumburi Village | Isibania | 3,318,957.20 | Work in progress |  |
|  | Renovation of doctor's house at Nyamanga dispensary | Kakrao | 607,970.00 | Work in progress |  |
|  | Completion of Nyamongo maternity | Kanyasa | 800,000.00 | Work in progress |  |
|  | Upgrading Riat dispensary | Kanyasa | 400,000.00 | Complete |  |
|  | Completion of Mikei Dispensary | Macalder/Kanyarwanda | 1,439.374.40 | Complete |  |
|  | Fencing of Kikongo | North Kadem | 600,000.00 | Complete |  |
|  | Fencing of Sayote | North Kadem | 600,000.00 | Complete |  |
|  | Fencing of Rae Kondiala Dispensary | North Kanyamkago | 1,000,000.00 | Work in progress |  |
|  | Completion of Alara Nyambija dispensary staff house | North Sakwa | 1,119.990 | Complete |  |
|  | Roofing of Itongo dispensary | Ntimaru East | 999,595.20 | Complete |  |
|  | Completion of Maternity Wing at Nyamagongwi dispensary | Nyabasi East | 1,999,550.00 | Complete |  |
|  | Completion and equipping of Kionyo dispensary | Nyabasi West | 1,998,819.20 | Work in progress |  |
|  | Completion of Kamilonde dispensary | South Kamagambo | 1,000,000.00 | Work in progress |  |
|  | Completion of Achuth Yao Dispensary | South Kanyamkago | 1,739,116.00 | Complete |  |
|  | Facelifting of Ngisiru Dispensary and Construction of toilet | Tagare | 999,993.37 | Complete |  |
|  | Construction of Arombe Dispensary | Wasimbete | 1,399,997.00 | Complete |  |
|  | Completion of Magoto Dispensary | Wasweta II | 3,021,869.60.00 | Complete |  |
|  | Facelifting of Koringo dispensary | West Kanyamkago | 1,500,000.00 | Work in progress |  |
|  | Completion of Ringa Kodongo dispensary | West Sakwa | 2,298,946.00 | Work in progress |  |
|  | Completion of staff house at Siruti Dispensary | West Sakwa | 998,319.20 | Complete |  |
|  | Completion of Kosege Dispensary | Wiga | 1,499,819.76 | Complete |  |
|  | Proposed 4door Vip Pit Latrine and Fencing at Kebaroti Dispensary | Nyabasi West | 1,449,652.00 | Work in progress |  |
|  | Completion of Ang’ogo dispensary staff house | North Sakwa | 1,196,470.40 | Work in progress |  |
|  | Construction of VIP Pit Latrine at Agolo Muok Dispensary | Kachieng | 749,325.00 | Work in progress |  |
|  | Construction of VIP Pit Latrine at Riat Kong’ou Dispensary | Kanyasa | 749,105.50 | Complete |  |

#### 2.3.2.7 Lands, housing, Physical planning and Urban Development.

| Project Name and Location (Ward/Sub- County/ Countywide} | Description Of activities | Target | Achievement | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| Preparation Kehancha Municipality Local Physical and Land Use Development Plan |  | 2 | 1 | Ongoing |  |
| Preparation of Valuation roll for Rongo Sub-County Urban areas | Mapping of all the Urban Areas in Awendo Subcounty Data Collection | 2 | 1 | Ongoing |  |
| Compensation for Land | Purchase of land for projects implementation and Land Banking | 3 | 3 | Ongoing |  |

#### 2.3.2.8 Rongo Municipality

| Project name and Location (Ward/Sub- county/ Countywide} | Description of activities | Target | Achievement | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| Proposed Rongo Municipality Beautification Project | Construction of modern shoe shiner booths Installation of modern taxi shades Street landscaping and planting of ornamental tree seedlings Installation of public street benches Placement of sustainable waste bins Clearing of clogged drainage channels | 1 | 1 | ongoing |  |
| Proposed maintenance and Gravelling of Rongo Municipality Roads (Central Kamagambo ward; Rongo Sub-County) | Earth works, civil works, gravelling, | 11km | 9 km | Complete |  |

#### 2.3.2.9Awendo Municipality.

| Project name and Location (Ward/Sub- county/ Countywide} | Description of activities | Target | Achievement | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| Provision of Electrical Works at Awendo Modern Market | Install wiring, cable management systems, junction boxes, distribution boards, switchgear, and associated electrical hardware | 1 | 1 | 70% done |  |
| Proposed Construction of 2 Boda Boda Shades | Fabrication, supply and installation of boda boda shades | 1 |  | Completed |  |
| Provision of Feasibility Study Report | Define Project Scope, Conduct Market Analysis assess Technical Feasibility, Perform Financial Analysis, Review Legal and Regulatory Requirements, Evaluate Risks, Analyze Operational Feasibility, Develop Conclusions and Recommendations | 1 | 1 | completed |  |
| Proposed maintenance of Musanda-Nucleus Road | Grading and murraming | 1 | 1 | completed |  |

#### 2.3.2.10 Kehancha Municipality

| Project Name and Location | Description of Activities | Target | Achievement | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| Heavy Commercial Vehicle Park Fencing | Construction and fencing of vehicle park | 100% | 100% | Completed | Physical works complete; |
| Municipal Roads Improvement | Opening, grading, and gravelling of roads | 8.5 km | 8.5 km | Completed | Omome–Nyaitara Road opened, graded, and partially graveled |
| Municipal Roads Maintenance | Routine maintenance of motorable roads | 4.3 km | 4.3 km | Completed | Roads maintained/opened across key town routes |
| Street Cleaning and Drainage | Town area cleanup and drainage channels cleared | 25 acres / 3 km drainage | 30 acres / 0 km drainage | Partially implemented | Cleanup ongoing; drainage clearing not implemented |
| Municipal Office Construction | Construction of municipal office building | 100% planned works | 0% | Not started | S Not implemented due to funding constraints |

#### 2.3.2.11 Migori Municipality

| Project name and Location (Ward/Sub- county/ Countywide} | Description of activities | Target | Achievement | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| Construction of Migori Municipal Recreational Park. Suna central ward, Suna East Sub- County | Fencing, construction of Gate and Gate house, Gazebos a Ablution block. | 1 | 1 | Done |  |
| Construction of Shoe shiner Booths in (suna west and suna east sub county) | Construction and installation | 3 | 3 | Done |  |
| Maintainance and unclogging Municipal drainages | Unclogging, repairs, stone pitching | 2km | 2km | Done |  |
| Opening of municipal roads | Grading, murraming, putting culvuts and opening drainages | 3.4km | 3.4km | On-going |  |

#### 2.3.2.12 Office of the Governor

Governor’s office

| Project name and Location (Ward/Sub- county/ Countywide} | Description of activities | Target | Achievement | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| County headqaurtesr | Construction |  | Construction in process | 68% completed | Ongoing |
| GIS lab | Establishment |  | Ongoing | 65% completed | Ongoing |

ICT

| Project name and Location (Ward/Sub- county/ Countywide} | Description of activities | Target | Achievement | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| Internet Subcription for county HQ and sub-counties Across the county | Procurement Process | 25 | 100% | complete | Considered main project |
| Recruit ICT Officers Suna Central/Suna East | Procurement Process | 9 | 100% | complete | Considered main project |
| Purchase and Supply of Desktop Computers, Laptops Suna Central/Suna East | Procurement Process | 18 | 100% | complete | Considered main project |
| Purchase and Supply of Revenue automation Devices (POS) & Printers Suna Central/Suna East | Procurement Process | 200 | 100% | complete | Considered main project |
| Support and Maintenance of County and Public Service Board Websites Online application portal Suna Central/Suna East | Procurement Process | 2 | 100% | complete | Considered main project |
| Support and Maintenance of Human Resource Management System Suna Central/Suna East | Procurement Process | 3000 Staffs | 100% | complete | Considered main project |
| Support and Maintenance Electronic Document Management System Suna Central/Suna East | Procurement Process | 1 dprt | 100% | complete | Considered main project |
| Subscription and support of Microsoft Office 365 Suna Central/Suna East | Procurement Process | 200 users | 100% | complete | Considered main project |
| Purchase and Supply of Computers Consumables and Communication Devices Suna Central/Suna East | Procurement Process | Assorted | 100% | complete | Considered main project |
| Maintenance and repair o ICT offices Suna Central/Suna East | Procurement Process | Assorted | 100% | complete | Considered main project |
| Supply and delivery of Network Accessories Suna Central/Suna East | Procurement Process | Assorted | 100% | complete | Considered main project |

#### 2.3.2.15Roads, transport, public works and Infrastructural Development.

| No | Project name | Budgeted cost (kshs) | Project location (ward/ Sub-county) |
| --- | --- | --- | --- |
| 1. | Nyaigutu - komomange - gwikonge - ikerege - robarisia - gosoho - nyabokararange - kebobono road | 947,782,251 | Bukira central |
| 2. | Masaba bridge - hibwa - roturini –kwirambo - upepo - sgaegi - makorangoro road |  | Masaba |
| 3. | Nyabohanse - nyamwini - kumumwamu - motemorabu - rosabare - ngochoni - komosoko - matare - kengariso road |  | Komosoko |
| 4. | Gukiguku - ngisiru - tagare - komorege –tongeri - korogati - romaguha - nyambare road |  | Tagare |
| 5. | Alliance 1 - karosi - nyabikwi - kemakoba road |  | Bukira east |
| 6. | Isebania township roads |  | Isebania |
| 7. | Isebania - kundurumo - nasa road |  | Makerero |
| 8. | Manga - tebesi - kebaroti - remanyaki road. |  | Nyabasi west |
| 9. | Rongo-rairi-kangeso road |  | East kamagambo |
| 10. | Ntimaru - bongebo - canaan - seronga - jerusalem road |  | Ntimaru west |
| 11. | Kwiriba market - gwikuniri - okwahu - nguruna - jehova - dc’s residence - kegonga town - kugitimo market - merama ng’ombe - gwitonyi road |  | Nyabasi east |
| 12. | Itongo - waitacho - siabayi - makonge junction road |  | Ntimaru east |
| 13. | Access to magoto |  | Wasweta ii |
| 14. | Kanga onditi - kiasa - adera road |  | Kaler |
| 15. | Koweru - olando - othora - tulu road |  | Got kachola |
| 16. | Munyu - nyakongo - ndemra - orango - kuja ring road |  | Macalder |
| 17. | Okenge - orango - kanyadera - pom - sayote - adiel - ong’er - thimlich - odingo - osani road |  | North kadem |
| 18. | Kalwenje - nyamanga - mashpark - odendo - raguda road |  | Kachieng |
| 19. | Alendo - rabare sch - god keyo sch - nyasoko primary access road - odanya - nyar godjope stage school road |  | Kanyasa |
| 20. | Oruba - ragana selected roads |  | Oruba |
| 21. | Karodi - wasulwa - kikongo - mugabo road |  | Muhuru |
| 22. | God kweru - kujungwa - kokendi - kosege - otung - magacha - chung’ni - malera - kipingi road |  | Wiga |
| 23. | Manyera - nyabkemo - masaria - kodol - border road |  | Wasimbete |
| 24. | Obama - siany - obama centre - korero - sony - kopiyo road |  | Central sakwa |
| 25. | Jwelu - nyandoto sda - kokoko - kuja sda - pap kojwang - wath owang - purotuang - nyasore - angogo - wath - owang road |  | North sakwa |
| 26. | Anduong’o - siruti - lee - kamyawa secondary - kodeny road |  | West sakwa |
| 27. | Rabuor - siany - nyachebe - manyatta - sony junction road |  | South sakwa |
| 28. | Oinga - nyangweta - kuna road and installation of culverts at kojwang |  | North kamagambo |
| 29. | Karabare - south kamagambo - ndonyo - okumba - kamreri ring road - kolondo - north kanyajuok road |  | South kamagambo |
| 30. | Kasere - nyamuga primary - winyo - kimamra - kanyagito - ngodhe road |  | East kamagambo |
| 31. | Komboga- kokendo and access |  | Central kamagambo |
| 32. | Access to owich |  | Central kanyamkago |
| 33. | Taragweti - kabos - ondati - ongoro road |  | West kanyamkago |
| 34. | Kajino - nyaongo - nyamasare - ndege oriedo - mori road |  | North kanyamkago |
| 35. | Msunzu - kobare - oyani road |  | East kanyamkago |
| 36. | Lower edemba - edemba school - lwala ring road - sigiria road |  | South kanyamkago |
| 37. | Ogejo - banana - kombura - banana - onding’mon - onyalo - blueshine - nyasare - apida - kasalah - midoti - dugna - kadika - kolembe road |  | Central suna |
| 38. | Ayego - yadh ngima - marienga - alara - siling road |  | God jope |
| 39. | Warisia - ting’na - vialo - korwa - kikoma - rayudhi - ugari road |  | Kakrao |
| 40. | Opasi - anglican - kabila - radienya - nyamongo school - kojea - kokoto road |  | Kwa |
| 42. | Rapogi - dede - kwoyo - luanda kawuor - oboke - nyasore - nyakuru - nyatambe- rinya- mulo roads |  | Awendo/rongo |
| 43. | Sakuri- kegonga- makararangwe - kiomakebe - kemakoba roads. |  | Kuria east |
| 44. | Kegonga - koromangucha - ntimaru- maeta- soteni - getontira roads |  | Kuria east |
| 45. | Karamu - ngisiru - gukiguku - tom mboya - nyanchabo - kubweye roads |  | Kuria west |
| 46. | Nyamagana - korobunyinge- nyamagagana - ikerege- kiomakebe - sorore roads |  | Kuria west |
| 47. | Bande - olasi - apilo- otati - raguda - otho- serena- got kachola- kanga onditi - nyandema roads |  | Nyatike |
| 48. | E109 kwoyo kodalo - a1 rongo - a1 marera - nyarach - ndege oriedo - matafari - kasere - ngodhe roads |  | Rongo |
| 49. | Bware - thimjope - oyani malo - kamin olewe - lela roads |  | Uriri |
| 50. | Kakrao - sibuoche - masaa - piny owacho - oyani a1 - gogo - kombe - sagegi roads |  | Suna east/uriri/kuria west |
| 51. | Uriri a1- nyabera |  | Uriri/awendo |
| 52. | Obware junction – alendo |  | Kanyasa |
| 53. | Ranen- otacho- ogwamrondo- kindu |  | Awendo |
| 54. | Migori- macalder- ochieng- orwa- magina- slaughter |  | Suna east/nyatike |
| 55. | Access to chacha moronya |  | Makerero |
| 56. | Access to guchishere |  | Gokeharaka |
| 57. | Access to itutu- mitiniti |  | Ntimaru east |
| 58. | Access to kembeho |  | Masaba |
| 59. | Access to koweru- sagenya |  | Got kachola |
| 60. | Access to piny- nyadundo |  | East kamagambo |
| 61. | Access to sere- komuto |  | South kamagambo |
| 62. | Access to ombasa |  | West sakwa |
| 63. | Awendo-kanyimach road |  | Awendo/rongo |
| 64 | Other assorted roads and structures |  | County |
| 65 | Acuth- corona foot bridge |  | Uriri |

#### 2.3.2.16 Trade Tourism, Industry,market and cooperative Development.

| Project name and Location (Ward/Sub-county/Countywide} | Description of activities | Target | Achievement | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| Supply and Delivery of Motorcycles ; East Kanyamkago | Supply | 3 | 3 | Delivered |  |
| Proposed Construction of Bodaboda Sheds at Ikerege Junction, Komoko, Kugitura, Komomange and Nyabokarange; Bukira Central | Construction | 4 | 4 | Complete |  |
| Supply and Delivery of Branded Diaries and Pens; Hqtrs | Supply | 100% | 100% | Delivered |  |
| Proposed Construction of Bodaboda Sheds; Isibania | Construction | 3 | 3 | Complete |  |
| Proposed Construction of Kojwang’ Market Shade North Kamagambo | Construction | 1 | 1 | Complete |  |
| Proposed Completion of Kugitimo Market Shade | Construction | 1 | 1 | Complete |  |
| Proposed Construction of Bodaboda Sheds t Opasi and Kisindi; Kwa | Construction | 2 | 2 | Complete |  |
| Proposed Construction of Bodaboda Sheds; Masaba; | Construction | 3 | 3 | Complete |  |
| Proposed Completion of Masangora Market Shade | Construction | 1 | 1 | Complete |  |
| Construction of Proposed Construction of Pit Latrine at Mikei ; Macalder Kayarwanda | Construction | 1 | 1 | Complete |  |
| Proposed Construction of Mukuro Market Shade; Wiga | Construction | 1 | 1 | Complete |  |
| Proposed Construction of Bodaboda Sheds at Alara Nyambija, Saria and Ranen Mision; North Sakwa | Construction | 3 | 3 | Complete |  |
| Proposed Construction of Bodaboda Sheds At Kwiriba, Getongoroma and Kwigena; Nyabasi East | Construction | 3 | 3 | Complete |  |
| Proposed Completion of Waterborne Toilet at Posta Ground; Suna Central | Construction | 1 | 1 | Complete |  |
| Proposed Installation of Integrated Solar Streetlights at Okusu Market; South Kamagambo | Construction | 1 | 1 | Complete |  |
| Proposed Construction of Olasi Market Shade; Kaler | Construction | 1 | 1 | Complete |  |
| Supply and Delivery of Printing Papers; Hqtrs | Supply | 100% | 100% | Delivered |  |
| Proposed Completion of Senta Market Shade; Nyabasi East | Construction | 1 | 1 | Complete |  |
| Proposed Construction of Awendo Shoe Shiner Shade and Bodaboda Shed; Central Sakwa | Construction | 2 | 2 | Complete |  |
| Proposed Construction of Bodaboda Sheds; South Kanyamkago | Construction | 2 | 2 | Complete |  |
| Proposed Construction of Bodaboda Sheds at Komorege, Tongeria and Mabera; Tagare | Construction | 3 | 3 | Complete |  |
| Supply and Delivery of Staff Uniforms; Hqtrs | Supply | 100% | 100% | Delivered |  |
| Supply and Delivery of Calibration And Instrumentation Equipment; Hqtrs | Supply | 3sets | 3sets | Delivered |  |
| Proposed Construction of Bodaboda Sheds at Graca and Catholic; Central Kamagambo | Construction | 2 | 0 | Complete |  |
| Supply and Delivery of County Business Assessment Forms; Hqtrs | Construction | 100% | 100% | Complete |  |
| Proposed Construction of Bodaboda Sheds at Alara, Oyuma and Wasio Junction; GodJope | Construction | 3 | 3 | Complete |  |
| Printing and Publishing of both Tourism Guide and Investment Opportunity Booklets; Hqtrs | Supply | 100% | 100% | Delivered |  |
| Proposed construction of boda boda shed at Kangeso Centre; East Kamagambo | Construction | 1 | 0 | Complete |  |
| Proposed Construction of Bodaboda Sheds at Kogore and Nyagod Jope School Junction; Kanyasa | Construction | 2 | 2 | Complete |  |
| Proposed Construction of Bodaboda Shed at Lifecare; Oruba Ragana | Construction | 1 | 1 | Complete |  |
| Proposed Construction of Masebe Market Shade; Makerero | Construction | 1 | 0 | Complete |  |
| Proposed Construction of Masebe Toilet; Makerero | Construction | 1 | 1 | Complete |  |
| Proposed Construction of Mapera Market Shade; Suna Central | Construction | 1 | 0 | Complete |  |
| Supply and Delivery of Mobile Phones; Hqtrs | Supply | 2 | 2 | Delivered |  |
| Proposed Construction of Bodaboda Sheds at Itonge, Taragai and Wangirabose; Ntimaru East | Construction | 3 | 3 | Complete |  |
| Proposed Fencing of Opapo Cattle Auction Ring; East Kamagambo | Construction | 1 | 1 | Complete |  |
| Supply and Delivery of Motorcycles for Trade Department; Hqtrs | Construction | 3 | 3 | Complete |  |
| Supply and Delivery of Sanitary and Cleaning materials and Services;Hqtrs | Supply | 100% | 100% | Delivered |  |
| Proposed construction of boda boda sheds Lwanda And Tuk Centre;North Kadem | Construction | 2 | 2 | Complete |  |
| Supply and delivery of Assorted Stationery; Hqtrs | Construction | 100% | 100% | Complete |  |
| Proposed construction of bodaboda Shed at Kibumburi; Waswetta II | Construction | 1 | 0 | Complete |  |
| Proposed construction of Koweru Market Shade; Got Kachola | Construction | 1 | 1 | Complete |  |
| Proposed Construction of Waterborne Toilet at Sori Bus Park; Kachieng | Construction | 1 | 0 | Complete |  |
| Proposed Construction of Kikongo Toilet ; Muhuru | Construction | 1 | 1 | Complete |  |
| Proposed Construction of Bodaboda Sheds At Chaguo Lako, Karosi and Township; Bukira East | Construction | 3 | 3 | Complete |  |

#### 2.3.2.17 Water and Energy

| Projects name and Location (Ward/Sub- County/Countywide) | Description of activities | Target | Achievement | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| Proposed equipping and piping at Kabola Water Project in Central Sakwa Ward, Awendo Sub County. | Equipping and pipeline extension | 1 | Equipped and extended. Operational | 100% complete | Operational |
| Proposed equipping and piping at Kokore Water Project in Central Sakwa, Awendo Sub County | Equipping and pipeline extension | 1 | Equipped and operational | 100% complete | Operational |
| Proposed drilling of Nyakuru borehole In North Sakwa ward, Awendo Sub County | Drilling, test pumping and water quality assessment | 1 | Dry borehole struck | 50% complete | New site to be surveyed |
| Piping and water tank for Rinya Market Toilet in South Sakwa ward, Awendo Sub County | Pipeline extension and installation of 10m3 tank | 1 | Completed and operational | 100% complete | Operational |
| Proposed equipping of Manyatta borehole in South Sakwa ward, Awendo Sub County | Equipping with solar powered pumping system, 10M3 tank | 1 | Completed and operational | 100% complete | Operational |
| Proposed overhaul of 2No. pumping sets at Awendo Water Supply in South Sakwa ward, Awendo Sub County | Overhaul of the pumping sets | 2 | Overhaul of the pumping sets done and faulty parts replaced | 100% complete | Faulty parts replaced |
| Proposed spring protection works of Kojwang' and Kamuga springs in South Sakwa ward, Awendo Sub County | Spring protection works | 2 | 2No. springs protected | 100% complete | Operational |
| Proposed spring protection of Kamola and Kogina springs and rehabilitation of Agongo Hill Water Spring in West Sakwa ward, Awendo Sub County | Spring protection and rehabilitation works | 3 | 2No. springs protected and Agongo Hill Spring Water Project rehabilitated | 100% complete | Operational |
| Supply and Delivery of 10,000Ltrs Tanks countywide | Supply and delivery of tanks in all the 40 wards 1No. each | 20 | 15No. out of the 20No. delivered and branded | 75% complete | Delivered but not yet distributed |
| Supply and Delivery of 10,000Ltrs Tanks countywide | Supply and delivery of tanks in all the 40 wards 1No. each | 20 | 15No. out of the 20No. delivered and branded | 75% complete | Delivered but not yet distributed |
| Proposed equipping of Nyamaranya borehole in Gokeharaka Getambweka ward, Kuria East Sub County | Equipping works | 1 | Equipped and operational | 100% complete | Operational |
| Proposed drilling of Remanyanki Primary School borehole in Nyabasi West ward, Kuria East Sub County | Drilling, test pumping and water quality assessment | 1 | Site changed to Tebesi primary school Drilled and capped | 60% complete | Recommended depth not yet attained |
| Proposed protection of Kegetene spring In Ntimaru East Ward, Kuria East Sub County | Spring protection works | 1 | Protected and operational | 100% complete | Operational |
| Supply of water tank at Matare Boarding and Kwibancha Primary Schools in Ntimaru West Ward, Kuria East Sub County | Supply of 2No. 10,000litres uPVC tanks | 2 | Delivered and installed | 100% complete | Supplied and installed |
| Supply of water tank at Kongori, Nyamotambe and Kwihemba Primary Schools in Nyabasi East Ward, Kuria East Sub County | Supply of 3No. 10,000litres uPVC tanks | 2 | Supplied and installed | 100% complete | Supplied and installed |
| Proposed equipping of Bagdad borehole in Isibania Ward, Kuria West Sub County | Equipping works | 1 | Equipped and operational | 100% complete | Operational |
| Proposed drilling of Kengori borehole in Makerero Ward, Kuria East Sub County | Drilling, test pumping and water quality assessment | 1 | The contractor did not mobilize. Department to consider terminating the contract. | Not yet drilled |  |
| Proposed rehabilitation of Nyametaburo Water Project in Makerero Ward, Kuria East Sub County | Rehabilitation works | 1 | The contractor did not mobilize. Department to consider terminating the contract. | No progress |  |
| Proposed spring protection at Nyametembe in Makerero Ward, Kuria East Sub County | Spring protection works | 1 | Protected and operational | 100% complete | Operational |
| Proposed equipping and piping of Nyanchabo Borehole in Masaba Ward, Kuria East Sub County | Equipping and pipeline extension | 1 | Equipped and operational | 100% | Operational |
| Proposed digging of Water pan at Nyakerere in Nyamosense Komosoko, Kuria West Sub County | Spring protection works | 1 | Pond found to be a spring and protected | 100% complete | Operational |
| Proposed equipping of Nyabohanse borehole in Nyamosense Komosoko, Kuria West Sub County | Equipping works | 1 | Equipped and operational | 100% complete | Operational |
| Proposed drilling of Apilo Center borehole in Got Kachola, Nyatike Sub County | Drilling, test pumping and water quality assessment | 1 | Drilled and capped | 100% complete | Drilled and capped |
| Proposed drilling of Pengle Dispensary borehole in Got Kachola, Nyatike Sub County | Drilling, test pumping and water quality assessment | 1 | Two dry boreholes struck. | 100% complete | Alternative option to be explored |
| Proposed drilling of Ratieny borehole in Got Kachola, Nyatike Sub County | Drilling, test pumping and water quality assessment | 1 | Drilled and capped | 100% complete | Drilled and capped |
| Proposed Repair of Hoho and Sidika Handpump in Kachieng ward, Nyatike Sub County | Repair of handpump | 2 | Hoho hand pump repaired | 100% complete | One hand pump repaired |
| Proposed distribution and reticulation of Nyamache Water Project in Kaler ward, Nyatike Sub County | Extension of pipeline works | 1 | Completed and operational | 100% complete | Operational |
| Proposed equipping and Upgrading of Kakodo borehole in Kaler ward, Nyatike Sub county | Equipping works | 1 | Completed with additional funding from CARE International in Kenya and operational | 100% complete | Operational |
| Proposed Maintenance of Bondo Kosiemo, Aringo borehole repair and Kogore Pundo spring protection in Kanyasa ward, Nyatike Sub county | Borehole repair works | 3 | Repair works completed and all the three facilities operational | 100% complete | Bondo Kosiemo and Aringo boreholes repaired. Pundo Kogore shallow well cleaned and deepened |
| Proposed equipping of Munyu borehole in Macalder Kanyarwanda ward, Nyatike Sub County | Equipping works | 1 | Equipped and operational | 100% complete | Operational |
| Proposed equipping of Ibencho borehole in Muhuru ward, Nyatike Sub county | Equipping works | 1 | Equipped and operational | 100% complete | Operational |
| Proposed equipping of Tuk borehole North Kadem ward, Nyatike Sub County | Equipping works | 1 | The contractor only mobilized to site. |  |  |
| Proposed repair and distribution pipeline at Rongo Water Supply in Central Kamagambo ward, Rongo Sub County | Repair and pipeline extension | 1 | Completed and operational | 100% complete | Rehabilitated to restore dormant conncetions in Rongo town |
| Proposed Spring Protection works at Kanyawendo and DRC in Central Kamagambo ward, Rongo Sub county | Spring Protection Works | 2 | 2No. springs protected | 100% complete | Operational |
| Proposed spring protection works at Wi Rabolo, Tin and Kokumu springs in South Kamagambo ward, Rongo Sub County | Spring Protection Works | 3 | 3No. springs protected | 100% complete | Operational |
| Proposed Repair of Distribution pipeline from Nyarongi to Nyikendo Centre in Kakrao Ward, Suna East Sub County | Repair of pipeline works | 1 | Completed and functional | 100% complete | Distribution mains to Nyarongi rehabilitated |
| Kamatete Spring Protection- Fencing and construction of Cattle Trough in God Jope Ward, Suna East Sub County | Spring protection and appurtenant structures works | 1 | Completed and functional | 100% complete | Operational |
| Drilling of borehole and purchase of submersible pump at Phelgona Primary School borehole in Kakrao Ward, Suna East Sub County | Drilling, development, test pumping, water quality assessment and procurement of submersible pump | 1 | Drilled and capped. Submersible pump complete with all accessories in the CDW’s office | 100% complete | Equippingtto be completed in 2025/2026FY |
| Proposed Roof Catchment System at Radienya Primary School in Kwa Ward, Suna East Sub County | Installation of roof catchment structures | 1 | Supplied and installed | 100% complete | Supplied and installed c/w guttering |
| Proposed equipping of Kadika borehole in Suna Central Ward, Suna East Sub County | Equipping works | 1 | Equipped and operational | 100% complete | Operational |
| Proposed servicing and repair of new Ombo borehole scheme in Suna Central Ward, Suna East Sub County | Borehole servicing and repair works | 1 | Completed and operational | 100% complete | Serviced and repaired to operational status |
| Proposed drilling of Milimani borehole inOruba Ragana Ward, Suna West Sub County | Drilling, development, test pumping, water quality assessment | 1 | Only hydrogeological survey done |  |  |
| Proposed equipping of Milimani borehole in Oruba Ragana Ward, Suna West Sub County | Equipping works | 1 | Borehole not yet drilled | No progress | The department to consider terminating this contract |
| Proposed extension of Nyamome pipeline in Oruba Ragana Ward, Suna West Sub County | Pipeline extension works | 1 | Completed and operational | 100% complete | Implemented to reduce the water fetching distance for Oruba Karoko community |
| Proposed rehabilitation of Soko Ogwedhi spring in Oruba Ragana Ward, Suna West Sub County | Rehabilitation of spring | 1 | Completed and operational | 100% complete | Rehabilitated to improve on the quality of water from this source |
| Proposed drilling and equipping of Ririba borehole in WasimbeteWard, Suna West Sub county | Drilling, development, test pumping, water quality assessment and equipping works | 1 | Contractor did not mobilize. Department to consider terminating the contract. | No Progress |  |
| Proposed drilling of Kadongo borehole in WasimbeteWard, Suna West Sub county | Drilling, development, test pumping and water quality assessment | 1 | Drilled and equipped with submersible pump | 100% complete | Drilled and equipped |
| Proposed drilling of Maweni Secondary School borehole in WasimbeteWard, Suna West Sub county | Drilling, development, test pumping and water quality assessment | 1 | Drilled and capped | 100% complete | Drillied and capped |
| Proposed equipping of Kadongo boreholeWasimbeteWard, Suna West Sub county | Equipping works | 1 | Equipped and operational | 100% complete | Operational |
| Proposed drilling of Kibumburia area borehole in Wasweta II, Suna West sub-county | Drilling, development, test pumping and water quality assessment | 1 | Contractor did not mobilize. Department to consider terminating the contract. | No Progress |  |
| Proposed drilling of Chamabare borehole in Wiga ward, Suna West sub-county. | Drilling, development, test pumping and water quality assessment | 1 | Only hydrogeological survey carried out | Not yet Drilled |  |
| Proposed drilling of Rombe borehole in Central Kanyamkago ward, Uriri sub-county. | Drilling, development, test pumping and water quality assessment | 1 | Only hydrogeological survey carried out | Not yet Drilled |  |
| Proposed drilling of Wikodongo borehole in East Kanyamkago ward, Uriri sub-county. | Drilling, development, test pumping and water quality assessment | 1 | Drilled and equipped | 100% complete | Operational |
| Proposed spring protection work at Ochiko Ite in East Kanyamkago, Uriri sub-county | Spring protection works | 1 | Completed and operational | 100% complete | Operational |
| Proposed equipping and distribution of Maraga borehole in North Kanyamkago, Uriri sub-county | Equipping works | 1 | Equipped and operational | 100% complete | Operational |
| Proposed spring protection works for 5No. springs in South Kanyamkago ward, Uriri Sub-county. | Spring protection works | 5 | Soweto, Katwenya, Kangoro, Kobinga and Komollo springs protected and operational | 100% complete | Soweto, Katwenya, Kangoro, Kobinga and Komollo springs protected and operational |
| Proposed overhaul of 1 No. pumping set at Oyani Treatment Plant in South Kanyamkago ward, Uriri Sub-county | Overhaul pumping set | 1 | Pumping set overhauled and faulty parts replaced | 100% complete | Faulty parts replaced |
| Proposed drilling and equipping of Dago borehole in West Kanyamkago ward,Uriri Sub-county | Drilling, development, test pumping, water quality assessment and equipping works | 1 | Drilled, equipped and operational | 100% complete | Completed and operational |
| Proposed installation of solar streetlights at Ayego in North Kanyamkago ward,Uriri Sub-county | Installation of solar streetlights | 5 | Completed and operational | 100% complete | Operational |
| Proposed installation of 12No. integrated solar streetlights within Kanyasa Ward,Nyatike Sub-county | Installation of solar streetlights | 12 | Completed and operational | 100% complete | Operational |
| Proposed installation of solar floodlights at Purotwang in North Sakwa Ward, Awendo Sub-county | Installation of solar floodlights | 1 | Completed and operational | 100% complete | Operational |
| Proposed installation of solar powered floodlights at Sori in Kachieng ward,Nyatike Sub-county | Installation of solar floodlights | 1 | Completed and operational | 100% complete | Operational |
| Proposed installation of solar powered floodlights at Masaba in Tagare Ward,Kuria West Sub-county. | Installation of solar floodlights | 1 | Completed and operational | 100% complete | Operational |
| Proposed supply and delivery of solar streetlights/floodlights fittings for minor repairs Countywide | supply and delivery of solar streetlights/floodlights fittings | 11 | Delivered for use | Supplied | Delivered |
| Proposed installation of solar streetlights at Jwelu, Chong Yamo and Kogema in North Sakwa Ward | supply and delivery of solar streetlights/floodlights fittings | 1 | Completed and operational | 100% complete | Operational |
| Proposed repair of 20No. solar streetlights within Migori County in all Wards County Wide | Repair of solar streetlights | 20 | Completed and operational | 100% complete | Operational |
| Proposed repair and maintenance of solar streetlights within the County in all Wards Countywide. | Repair and maintenance of solar streetlights | 40 | Completed and operational | 100% complete | Operational |
| Supply and delivery of electrical tools in the County | Supply and delivery of electrical tools | 1 | Delivered for use. | Supplied | Operational |
| Installation of transformer and distribution of power At St. Kizito in Bukira Central Ward,Kuria West Sub-county. | Installation of transformer and distribution of power | 1 | County Government of Migori to make direct payment to KPLC. 50No. households expected to be connected | The project is being implemented by KPLC | Operational |
| Proposed installation of green streetlights 14 No. integrated solar streetlights in Oruba Ragana and Bukira East ward,Suna West and Kuria West Sub-county. | Installation of green streetlights and integrated solar streetlights | 14 | Completed and operational | 100% complete | Operational |
| Proposed installation of solar floodlights at Ngira Beach in Kanyasa ward, Nyatike Sub-county | Installation of solar floodlights | 1 | Completed and operational | 100% complete | Operational |
| Proposed installation of solar streetlights at Got Kachola Ward, Nyatike Sub-county | Installation of solar streetlights | 3 | Completed and operational | 100% complete | Operational |
| Repair of 4 No. solar powered floodlights within Migori County (Kachieng, Muhuru and Bukira East wards) in Nyatike and Kuria West Sub-counties | Repair of solar powered floodlights | 4 | Completed and operational | 100% complete | Operational |
| Repair of grid powered floodlights within Migori County (Kaler, Suna Central, Oruba Ragana, Central Kamagambo and Bukira East wards) in Nyatike, Suna East, Suna West, Rongo and Kuria West Sub-counties. | Repair of grid powered floodlights | 5 | Completed and operational | 100% complete | Operational |
| Proposed installation of streetlight advertisement boxes within Migori in Suna Central and Oruba Ragana ward, Suna East and Suna West Sub-counties. | Installation of streetlight | 10 | Completed and operational | 100% complete | Operational |
| Proposed installation of 5 No. integrated solar streetlights at Odingo Centre in East Kamagambo (Odingo, Kongou, Kal Akuodhi, Kangeso) Ward,Rongo Sub-county | Installation of integrated solar streetlights | 5 | Completed and operational | 100% complete | Operational |
| Proposed installation of floodlights at Kadianga Market in North Kamagambo, Rongo sub county | Installation of floodlights | 1 | Completed and operational | 100% complete | Operational |
| Proposed installation of integrated Solar floodlights at Winter in Central Kamagambo ward, Rongo subcounty. | Installation of integrated Solar floodlights | 1 | Completed and operational | 100% complete | Operational |